## Stope
Long-Hole Stope Evaluation
Version: December 18, 2002
1.0 - Physical parameters of the stope
Typical stope
|  | Vertical height (m) | [5 empty] | Swell
Length (m) | Width (m) |  | Dip (°) | Slope distance (m) |  |  | Density (t/m³) | factor
92.5 | 3 | 60 | 90 | 60 |  |  | 3.75 | 1.38
Ore (reserves) |  | Milled ore
Tonnage | Grade (g/t) | Tonnage | Grade (g/t) | Dilution
62437.5 | 4.5 | 66808.125 | 4.271 | 7%
2.0 - Stope development
2.1 - Development parameters
|  | Dimensions |  |  |  | M advanced /shift | M advanced /manshift
|  | Width | Height | T/m advanced | # of men
Drift 1 |  | 3.7 | 3.2 | 32.56 | 3 | 2.6 | 0.86667
Drift 2 |  | 3.7 | 3.2 | 32.56 | 3 | 2.7 | 0.9
Drawpoints |  | 3 | 2.7 | 0 | 2 | 1.8 | 0.9
Timbered raise |  | 1.8 | 2.4 | 0 | 2 | 1.8 | 0.9
Alimak raise |  | 2.7 | 2.7 | 20.0475 | 2 | 2.3 | 1.15
Open raise |  | 1.8 | 2.4 | 0 | 2 | 2.3 | 1.15
Sub-level 1 |  | 3 | 2.6 | 29.25 | 3 | 2.9 | 0.96667
Sub-level 2 |  | 4 | 2.6 | 39 | 3 | 2.9 | 0.96667
Sub-level 3 |  | 6 | 3.2 | 72 | 3 | 2.9 | 0.96667
2.0 - Stope development (cont'd)
2.2 - Required development (see "Development" sheet)
BY THE UPPER | Ore |  |  |  | Waste |  | Total
LEVEL | Length | Tonnes/meter | Dilution | Diluted grade (g/t) | Length | Tonnes/meter | Length | Tonnes
Upper drifts | 92.5 | 29.3 | 5% | 4.29 |  |  | 92.5 | 2710
Stope access | 7.5 | 29.3 | 5% | 4.29 |  |  | 7.5 | 220
[7 empty] | 0 | 0
TOTAL | 100 | 29.3 |  | 4.29 | 0 | 0 | 100 | 2930
BY THE LOWER | Ore |  |  |  | Waste |  | Total
LEVEL | Length | Tonnes/meter | Dilution | Diluted grade (g/t) | Length | Tonnes/meter | Length | Tonnes
Lower drifts | 92.5 | 29.3 | 5% | 4.29 |  |  | 92.5 | 2710
Drawpoints | [6 empty] | 0 | 0
Main raise | [6 empty] | 0 | 0
Slot raise | [6 empty] | 0 | 0
Opening for Alimak | [6 empty] | 0 | 0
Opening for Alimak | [6 empty] | 0 | 0
Sub-level 1 | 7.5 | 29.3 | 5% | 4.29 |  |  | 7.5 | 220
Sub-level 2 | [6 empty] | 0 | 0
Sub-level 3 | [6 empty] | 0 | 0
Sub-level 4 | [6 empty] | 0 | 0
Stope access | [6 empty] | 0 | 0
[7 empty] | 0 | 0
TOTAL | 100 | 29.3 |  | 4.29 | 0 | 0 | 100 | 2930
2.3 - Development schedule parameters
Number of shifts/day |  |  | 2 | shifts
Number of working days/month |  |  | 20.8 | working days
Contingency |  |  | 10%
2.4 - Calculation of the development time
Number of
Upper level |  | Length | # of shifts/day | Advances/shift | # required days | installation days | Total | Sequence |  |  | 1 | 2 | 3
Upper drifts |  | 92.5 | 2 | 2.75 | 17 | 0 | 17 | 2 | 2 | 17 | 0 | 17 | 0
Stope access |  | 7.5 | 2 | 2.75 | 2 | 2 | 4 | 1 | 1 | 4 | 4 | 0 | 0
|  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | working days |  |  |  | 4 | 17 | 0
21
Number of
Lower level |  | Length | # of shifts/day | Advances/shift | # required days | installation days | Total | Sequence |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Lower drifts |  | 92.5 | 2 | 2.75 | 17 | 0 | 17 | 2 | 2 | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Drawpoints |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Main raise |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Slot raise |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening for Alimak |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Opening for Alimak |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 1 |  | 7.5 | 2 | 2.75 | 2 | 2 | 4 | 1 | 1 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 2 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 3 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 4 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stope access |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | working days |  |  |  | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21
|  |  | Time + | Contingency = | TOTAL |  | DEVELOPMENT TIME
Lower level |  |  | 21 | 2.1 | 23.1 | working days | (WORKING DAYS)
Upper level |  |  | 21 | 2.1 | 23.1 | working days | 24
3.0 - Stope production calculation
3.1 - Mining parameters
Productivity |  |  | 41 | tonnes/manshift
Number of men/shift |  |  | 4 | men
Number of shifts/day |  |  | 2 | shifts
Number of working days/month |  |  | 20.75 | working days
Milling days/year |  |  | 365 | working days
3.2 - Stope life calculation
Broken tonnes/day (in production) |  |  | 328 | tonnes
Mucking capacity during the blasting phase
a) muck the excess due to the swell |  |  | 124.64 | tonnes/day
b) muck to equipment capacity |  |  | 333 | tonnes/day | Stope life (production)
[5 empty] | 190 | working days | 9.1566 | months
Mucked tonnes/day (in production) |  |  | 260 | tonnes
Remaining tonnage inside the stope |  |  | 17198.8393 | tonnes
- Lost ore between drawpoints |  |  | 50 | tonnes
= Recovered tonnage inside the stope |  |  | 17148.8393 | tonnes | Time required to muck the rest of the stope
Tonnes/shift (final mucking of the stope) |  |  | 166.5 | tonnes/shift | 51 | working days | 2.4578 | months
3.3 - Calculation of production with relation to the number of active stopes
In order to maintain a constant production rate, the number of production stopes must be proportional to the number of stopes in the final mucking phase.
Assuming that all stopes have the same configuration, the production time of 190 days divided by the final mucking time of 51 days will allow you to calculate
an optimum ratio of the production time over the final mucking time which is equal to |  |  |  |  | 3.73 | to maintain a maximum productivity with
a minimum number of active stopes.
Which means that the production will be optimal if 3.73 stopes are active for each stope in the final mucking phase.
|  |  |  | Actual tonnage/day |  |  | Average milled tonnage/day (annual basis)
Number of stopes (production phase) |  |  | 2 | 520 |  |  | 355
Number of stopes (final mucking phase) |  |  | 0.53619 | 179 |  |  | 122
|  |  |  | 699 |  |  | 477
Note: The calculations presume that the work schedule is the same for production and ore mucking.
3.3.1 - Calculation of the number of stopes in the development phase to maintain the production rate
In order to maintain a constant production rate, the number of production stopes must be proportional to the number of stopes in the development phase.
Assuming that all stopes have the same configuration, the production time of 190 days divided by the development time of 24 days will allow you to calculate
an optimum ratio of the production time over the development time which is equal to |  |  |  |  | 7.92 | .
Which means that the production will be optimal if 7.92 stopes are active for each stope in the development phase.
Average milled ore tonnage/day (annual basis)
Number of stopes (production phase) |  |  | 2 | Actual ore tonnage/day
Number of stopes (development phase) |  |  | 0.25253 | 62 |  |  | 42
Note: The calculations presume that the work schedule is the same for production and development.
4.0 - Backfilling
4.1 - Calculation of the volume to backfill
Tonnes
Mined tonnage from the stope (dilution included) |  |  |  | 66548.8393
| Length | Width | Height | Tonnes
Drifts | 92.5 | 3.1 | 2.7 | 2903.3438
Drawpoints | 6 | 3.1 | 2.7 | 188.325
Others |  |  |  | 0
|  |  | Total tonnage | 69640.508 |  | Volume to backfill | 18570.8021 | m³
4.2 - Calculation of the time required to backfill
|  |  | Number of barricades |  | Number of days/barricade |  | Working days
- Construction of barricades |  |  | 1 |  | 5 |  | 5
- Backfilling time |  | Backfilling capacity (solid tonnes/hour) |  |  | 70 | tonnes/hour
|  | In situ backfill density |  |  | 2.2 | tonnes/m³
|  | Effective backfilling time per shift |  |  | 8 | effective hours/shift
|  | Number of required shifts |  |  | 72.9567 | shifts | Working days
|  | Number of shifts/day |  |  | 3 | shifts/day | 24.3189
- Total time required |  | 29.3189 | working days
ou
|  | 1.4096 | months | (in accordance with the development schedule entered in section 2.3)
5.0 - Compilation
DEVELOPMENT
|  | Waste |  | Ore |  |  | TOTAL
|  | Length (m) | Tonnes | Length (m) | Tonnes | Grade (g/t) | Length (m) | Tonnes
Drifts |  | 0 | 0 | 185 | 5421 | 4.29 | 185 | 5421
Drawpoints |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Raise |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level |  | 0 | 0 | 7.5 | 220 | 4.29 | 7.5 | 220
Other openings |  | 0 | 0 | 7.5 | 220 | 4.29 | 7.5 | 220
|  | 0 | 0 | 200 | 5861 | 4.29 | 200 | 5861
[6 empty] | 752 | ounces
MINED ORE CALCULATION FROM ORIGINAL RESERVES DURING STOPE DEVELOPMENT
|  | Diluted ore (Dev.) |  | Ore from reserves |  | Waste
|  | Tonnes | Grade (g/t) | Tonnes | Grade (g/t) | Tonnes
Main raise |  | 0 | 0 | 0 | 0 | 0
Slot raise |  | 0 | 0 | 0 | 0 | 0
Opening for Alimak |  | 0 | 0 | 0 | 0 | 0
Opening for Alimak |  | 0 | 0 | 0 | 0 | 0
Sub-level 1 |  | 219.75 | 4.29 | 209.2857 | 4.5045 | 10.4643
Sub-level 2 |  | 0 | 0 | 0 | 0 | 0
Sub-level 3 |  | 0 | 0 | 0 | 0 | 0
Sub-level 4 |  | 0 | 0 | 0 | 0 | 0
|  | 219.75 | 4.29 | 209.2857 | 4.5045 | 10.4643
[5 empty] | 28 | ounces
STOPE
[5 empty] | Tonnes | Grade (g/t) | Ounces
Length | 92.5 | meters | Reserves |  | 62228.2143 | 4.2702 | 7946
Width | 3 | meters | Dilution |  | 7%
Vertical height | 60 | meters | Lost ore between DP |  | 50 | 4.271 | 6
Dip | 90 | ° | Mill recovery |  |  | 96%
Density | 3.75 | tonnes/m³
[5 empty] | Tonnes | Grade (g/t) | Ounces
|  |  | Milled ore * |  | 66548.8393 | 3.99 | 7940
* The milled ore from the stope originates from the diluted geological reserves (section 1.0) minus the portion of the mined reserves
during stope development.
DEVELOPMENT + STOPE
[5 empty] | Tonnes | Grade (g/t) | Ounces
|  |  |  | Milled ore from development | 5861 | 4.29 | 752
|  |  |  | Milled ore from the stope | 66548.8393 | 3.99 | 7940
[5 empty] | 72409.8393 | 4.0142 | 8692
Note on D88: This percentage increases the development time (see cells E119 and E120)
Note on D161: Enter the number of active stopes in relation to the desired production level
Note on D142: Enter the mucking rate during the stope blasting phase
Note on C145: See "Development" sheet to determine the lost tonnage
Note on I93: Identify the critical path by entering different figures
Note on D127: See "Productivity_Long-Hole" file if you wish to verify the productivity for your operation
Note on B10: Measured perpendicularly to the vein
Note on C11: Height of the stope to be mined, including the sub-levels
Note on E17: Extra dilution to the one already included in the geological reserves. See "Stope_Dilution" file if you wish to verify your estimate.
Note on I101: Identify the critical path by entering different figures
H ver
D°
3rd drilling level or UPPER LEVEL
2nd drilling sub-level
lst drilling sub-level
Drop raises
Typical Long-Hole Stope
LOWER LEVEL

## Development
Version: December 18, 2002
Drawpoint parameters
Physical parameters
|  |  |  | Vertical height (m) |  | Density (t/m³) | Swell
- Typical stope |  | Length (m) | Width (m) |  | Dip (°) |  | factor
|  | 92.5 | 3 | 60 | 90 | 3.75 | 1.38
- Drawpoint parameters
Friction angle
Planned spacing (m) |  | Drawpoint width (m) |  | Length (m) | of the ore (°)
10 |  | 2.9 |  | 10 | 38
Drawpoints at both ends |  |  | No drawpoint at both ends |  |  | One drawpoint at one end
Number | Actual spacing |  | Number | Actual spacing |  | Number | Actual spacing
6 | 18.5 | meters | 5 | 18.5 | meters | 6 | 16.8182 | meters
Lost ore between drawpoints |  |  | Lost ore between drawpoints |  |  | Lost ore between drawpoints
Height (m) | Volume (m³) | Tonnes | Height (m) | Volume (m³) | Tonnes | Height (m) | Volume (m³) | Tonnes
6.094 | 784.3014 | 2131.2538 | 6.094 | 641.7011 | 1743.7531 | 5.437 | 624.3079 | 1696.4887
Raise configurations depending on its position in relation to the stope
Central raise in the ore
Vertical difference (m) |  | Dip (°) | Length (m) | Horizontal distance (m)
60 |  | 80 | 60.9256 | 10.5796
Central raise in the waste in a wall with regularly spaced sub-levels
RAISE
|  |  | Vertical difference (m) |  | Dip (°) | Density (t/m³) | T/m avanced | Raise length
|  |  | 60 |  | 80 | 2.9 | 10.6 | 60.9256
SUB-LEVELS
|  |  | Sub-level height | Sub-level width | Sub-level length | T/sub-level
|  |  | 2.4 | 1.8 | 6.8598 | 86
|  |  | Number of sub-levels |  | Actual spacing between sub-levels (m)
|  |  | 4 |  | 10.08
|  |  | Thickness of pillar between the raise and the stope |  |  | 6.7555 | meters
|  |  | Compilation | Sub-levels | Raise | TOTAL
|  |  | Length (m) | 10.8598 | 60.9256 | 71.7854
|  |  | Tonnes | 344 | 646 | 990
Cross-section
Raise in the ore at one end with sub-levels
RAISE
|  |  | Vertical difference (m) |  | Dip (°) | Density (t/m³) | T/m avanced | Raise length | Grade (g/t)
|  |  | 60 |  | 90 | 2.9 | 12.4 | 60 | 10
SUB-LEVELS
|  |  | Sub-level height | Sub-level width | Sub-level length | T/sub-level | Grade (g/t)
|  |  | 2.4 | 1.8 | 6.9 | 86 | 10
|  |  | Number of sub-levels |  | Actual spacing between sub-levels (m)
|  |  | 4 |  | 10.08
|  |  | Thickness of pillar between the raise and the stope |  |  | 6.9 | meters
|  |  | Compilation | Sub-levels | Raise | TOTAL
|  |  | Length (m) | 10.9 | 60 | 70.9
|  |  | Tonnes | 344 | 744 | 1088
Longitudinal view |  |  | Grade (g/t) | 10 | 10 | 10
Note on C14: If the drawpoint is still filled with ore, you must enter "0" in the drawpoint width
Spacing
Spacing
Spacing

## Drawing
Version: December 18, 2002
3rd drilling level or UPPER LEVEL
2nd drilling sub-level
1st drilling sub-level
Drop raises
Typical Long-Hole Stope
LOWER LEVEL