## Sub-level
SUB-LEVEL
Productivity
Version: May 14, 2004
1.0 - DIRECT FIXED ACTIVITIES PER SHIFT (outside the sub-level)
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  | NOTES
Cage (at beginning and end of shift) |  | 2 | 10 | 20
Travelling (shaft - refuge station - shaft) |  | 2 | 5 | 10
Other travelling delays |  |  |  | 0
Back and forth to sub-level |  | 4 | 10 | 40
Supervision |  | 1 | 15 | 15
Work planning |  | 1 | 10 | 10
Complete daily reports |  | 1 | 12 | 12
Lunch |  | 1 | 30 | 30
0
|  |  |  | 137 | minutes
|  |  |  | 2.2833 | hours/shift
2.0 - DIRECT FIXED ACTIVITIES PER STEP (inside the sub-level)
RELATED TO PREPARATION |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | RELATED TO GROUND |  | Frequency or Units | Time (min)/Unit | Total Time (min)
FOR SCRAPING | [5 empty] | SUPPORT
Clean hoist |  | 1 | 5 | 5 |  | Bring equipment and material |  | 1 | 10 | 10
Drill holes for eyebolts |  | 2 | 4 | 8 |  | Install setup platform |  | 1 | 5 | 5
Install eyebolts |  | 2 | 3 | 6 |  | Store material |  |  |  | 0
Hook pulleys and cable to eyebolts |  | 1 | 9 | 9 | [5 empty] | 0
Time delay because the chute is full |  | 1 | 2 | 2 |  |  |  |  | minutes/setup | 15
|  |  |  | 0 |  |  |  |  | hours/setup | 0.25
0
0
0
0
0
|  |  |  | 30 | minutes/scraping preparation with hoist
|  |  |  | 0.5 | hours/scraping preparation with hoist
2.0 - (cont'd) DIRECT FIXED ACTIVITIES PER STEP (inside the sub-level)
RELATED TO | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  |  |  | Frequency or Units | Time (min)/Unit | Total Time (min)
DRILLING |  |  |  |  | RELATED TO BLASTING
Prepare material | 1 | 5 | 5 |  | Bring explosives |  |  | 1 | 5 | 5
Store material | 1 | 5 | 5 |  | Bring and prepare material |  |  | 1 | 6 | 6
Remove setup platform |  |  | 0 |  | Store equipment and explosives |  |  | 1 | 5 | 5
|  |  | 0 |  | Connect the blast |  |  | 1 | 8 | 8
|  |  | 0 |  | Access verification |  |  | 1 | 5 | 5
|  | minutes/setup | 10 |  | Extra scaling |  |  | 1 | 5 | 5
|  | hours/setup | 0.16667 |  | Repair and install ventilation |  |  |  |  | 0
0
0
0
0
[9 empty] | minutes/blast | 34
[9 empty] | hours/blast | 0.56667
3.0 - DIRECT FIXED ACTIVITIES PER SUB-LEVEL (inside the sub-level)
RELATED TO CUTTING SUB-LEVELS
FROM THE RAISE |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | OTHER ACTIVITIES |  | Frequency or Units | Time (min)/Unit | Total Time (min)
(SEE STEPS 1 AND 2 IN DRAWING) | [5 empty] | PER SUB-LEVEL
|  |  |  | 0 |  | Geologists |  | 2 | 20 | 40
Enlarge raise |  | 4 | 300 | 1200 |  | Surveyors |  | 1 | 30 | 30
Extra ground support |  | 4 | 240 | 960 |  | Mechanics and electricians |  | 1 | 30 | 30
Manual face cleaning |  | 4 | 240 | 960 | [5 empty] | 0
Hoist installation |  |  |  | 0 | [5 empty] | 0
Bring up material |  | 1 | 60 | 60 | [5 empty] | 0
Construction of the landing |  | 1 | 120 | 120 |  |  |  |  | minutes | 100
Install ventilation |  |  |  | 0 |  |  |  |  | hours | 1.6667
0
0
0
|  |  |  | 3300 | minutes
|  |  |  | 55 | hours
Standard working steps in captive sub-level:
1 - Cut sub-levels from the raise (see section 3.0)
2 - Install hoist and build landing (see section 3.0)
3 - Excavate the first section with the hoist
4 - (optional) Bring in more performing equipment for drilling and/or mucking (Cavo 310, or other)
4.0 - DIRECT VARIABLE ACTIVITIES PER STEP (inside the sub-level)
4.1 - Dimensions
| Round |  |  | Sub-level |  |  | Cut parameters
| parameters |  |  | parameters |  |  | for the sub-level
See steps 1 and 2 in Drawing
| Drilled length | 1.8 |  | Length | 80 |  | Length | 6 | Equivalent length (m)
| Broken length | 1.7 |  | Height | 2.7 |  | Average height | 3 | 9.3
| Height | 2.7 |  | Average width | 1.8 |  | Average width | 2.5 | Ore density (t/m³)
| Width | 1.8 |  | # of rounds | 48 |  | Number of blasts | 4 | 2.95
| Tonnes | 25 |  | Tonnes | 1147 |  | Tonnes | 133
4.2 - Scaling
| minutes/ |  |  |  | total hours (sub-level)
Wash, scale and clean bootlegs | longitudinal m | hours
| 10 | 0.3 |  |  | 13.4
4.3 - Ground Support | [5 empty] | DRILLING PARAMETERS (support)
[6 empty] | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
|  | hours |  |  | hours | Time required for repositioning, changing drilling steel and bits, etc. per hole of 1.2 m (min) |  |  |  | 0.5
Drilling for support |  | 0.7 |  |  | 36.4
| installation time/bolt (min) |  |  |  |  | Total average time to drill a 1.2-m hole (min) |  |  |  | 2.66
|  | hours |  |  | hours
Installation of ground support | 8.5 | 1.7 |  |  | 88.4 | Average drilling rate |  |  |  | 27.0677
(screen included) |  | total hours |  |  | total hours | (drilled meters per hour/man/drill)
|  | 2.4 |  |  | 124.8
GROUND SUPPORT PARAMETERS
[8 empty] | Drilled length/bolt | Number of bolts/1.2 m advanced | Drilled meters/m advanced
[6 empty] | Roof pattern |  | 1.67 | 3 | 4.3
[6 empty] | Hanging wall pattern |  | 1.67 | 2 | 2.9
[6 empty] | Footwall pattern |  | 1.67 | 2 | 2.9
[9 empty] | 7 | 10.1
4.4 - Mucking or Scraping
| tonnes/hour | hours |  | tonnes/hour | hours
Mucking | 46 | 0.6 |  | 46 | 25
4.5 - Drilling | [5 empty] | DRILLING PARAMETERS (advance)
| drilled holes/round |  |  |  |  | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
| 33 |  |  |  |  | Time required for repositioning, changing drilling steel and bits, etc. per hole of 2.4 m (min) |  |  |  | 2
[6 empty] | Total average time to drill a 2.4-m hole (min) |  |  |  | 6.32
|  | meters |  |  | meters | Average drilling rate |  |  |  | 22.7848
Meters to drill |  | 59.4 |  |  | 2851.2 | (drilled meters per hour/man/drill)
|  | hours |  |  | hours |  | tonnes/drilled m
Time required for drilling (hours) |  | 2.7 |  |  | 125.2 |  | 0.42088
4.6 - Loading and Blasting |  | holes/blast |  |  |  | BLASTING PARAMETERS
|  | 27 |  |  |  |  | Hole diameter (mm) | 32 | Powder factor per round (kg/tonne)
| average time/ hole (min) |  |  |  | total hours (sub-level) |  | Explosive density (g/cc) | 1.01
hours
Clean and load holes | 1.3 | 0.8 |  |  | 41.6 | Kg of explosives/meter |  | 0.81229 | 1.93
Required explosives (kg) |  | 48 |  |  | 2214 |  | Number of blasts (sub-level) |  |  | 52
4.7 - Ventilation
(To use when blasting causes a delay during the shift or when the work schedule is 24 hours a day)
minutes required
Ventilation | /blast |  |  |  | total hours
(evacuation of fumes) |  |  |  |  | 0
5.0 - ROUND COMPILATION
TABLE OF REQUIRED HOURS PER ROUND
DIRECT ACTIVITIES
PER ADVANCE |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 0.25 | 0.16667 | 0.5 | 0.56667 | 0 | 0.032051 | 1.5154
DIRECT VARIABLE (hours) |  | 0.3 | 2.4 | 2.7 | 0.6 | 0.8 |  |  | 6.8
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 0.15 | 1.2 | 1.35 | 0.6 | 0.4 |  |  | 3.7
* The number of required hours is corrected according to the number of men entered in section 5.0. | [7 empty] | total : | 5.2154
+
[8 empty] | contingency (ventilation included) | 10%
[8 empty] | allocated time for contingency | 31.2923 | minutes
=
[8 empty] | total time required inside the sub-level (contingency included) | 5.8 | hours
+
[8 empty] | total time of direct fixed activities outside the sub-level | 2.2833 | hours
| REQUIRED NUMBER OF MEN | 2 | [6 empty] | =
| NUMBER OF HOURS PER SHIFT | 8 | <=> |  |  |  |  | total time required per advance | 8.0833 | hours
[8 empty] | occupation rate of the shift per advance | 101%
5.1 - CALCULATION OF THE POSSIBLE NUMBER OF ADVANCES PER SHIFT ACCORDING TO ENTERED DATA:
In this section, you can optimize your operating parameters to simulate your operation or to find
the required parameters to reach the desired performance.
|  | Number of hours per shift | 8
|  |  | - |  | total time required inside the sub-level (contingency included)
|  | Direct fixed time outside the sub-level/shift | 2.2833 |  |  |  |  | Possible number of advances per shift
=
|  | Available time inside the sub-level/shift | 5.7167 | / | 5.8 |  | = | 0.98563
Is it possible to blast during the shift? If no, change the parameters to obtain a round number
6.0 - SUB-LEVEL COMPILATION | [7 empty] | CHUTES, MANWAYS, CUT
DIRECT ACTIVITIES
PER SUB-LEVEL |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION |  | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 13 | 8.6667 | 26 | 29.4667 | 0 | 55 | 1.6667 | 133.8
DIRECT VARIABLE (hours) |  | 13.4 | 137.9294 | 139.9706 | 25 | 45.9765 |  |  |  | 362.2765
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 6.7 | 62.4 | 62.6 | 25 | 20.8 |  |  |  | 177.5
* The number of required hours is corrected according to the number of men entered in section 5.0. | [8 empty] | total : | 311.3
total
REQUIRED MANHOURS |  | 13.4 | 150.8 | 142.5333 | 102 | 100.5333 | 0 | 110 | 3.3333 | 622.6
REQUIRED MANSHIFTS |  | 1.675 | 18.85 | 17.8167 | 12.75 | 12.5667 | 0 | 13.75 | 0.41667 | 77.825
+
REQUIRED NUMBER OF MEN |  | 2 |  |  |  | with a contingency of | 10% |  | manshift contingency | 7.7825
NUMBER OF HOURS PER SHIFT |  | 8 | hours | [6 empty] | =
[9 empty] | required manshifts inside the sub-level | 85.6075
+
[9 empty] | required manshifts from direct fixed activities (outside the sub-level) | 34.1931
=
[9 empty] | total manshifts required | 119.8006
[8 empty] | with a performance of | 0.98563 | advance/shift
|  |  |  | From your best estimate, you can maintain | 0.94 | advance/shift
|  |  |  | which represents an occupation rate of the shift (contingency included) of | 95.37%
MANSHIFTS
| INSIDE THE SUB-LEVEL |  |  |  | OUTSIDE SUB-LEVEL | TOTAL |  |  | 1280 | tonnes
| PRODUCTIVE | CONTINGENCY | TOTAL (SUB-LEVEL) |  | FIXED
| 82.8586 | 8.2859 | 91.1445 |  | 36.4047 | 127.5492 | PRODUCTIVITY |  | 10.0353 | tonnes/manshift
| 64.96% | 6.496% | 71.46% |  | 28.54% | 100%
[9 empty] | 0.67425 | meter/manshift
Calculation of required manhifts with contingency |  |  | Calculation of number of shifts according to schedule |  |  |  | Calculation of number of shifts of direct fixed activities
Required manhours | 622.6 |  |  | Required manshifts with contingency | 85.6075 |  |  | Number of required shifts (schedule) | 59.9003
| / |  |  |  | / |  |  |  | x
Hours/shift | 8 |  |  | Available hours inside the sub-level | 5.7167 |  |  | Direct fixed hours/shift | 2.2833
| = |  |  |  | x |  |  |  | /
Required manshifts | 77.825 |  |  | Hours/shift | 8 |  |  | Hours/shift | 8
| + |  |  |  | / |  |  |  | =
Contingency | 10% |  |  | Men | 2 |  |  | Number of shifts of direct fixed activities (schedule) | 17.0965
| = |  |  |  | =
Required manshifts | 85.6075 |  |  | Number of required shifts (schedule) | 59.9003
with contingency
Calculation of total number of required manshifts
| Total number of required shifts | 59.9003
x
| Men | 2
=
| Required manshifts | 119.8006
| with a performance of | 0.98563 | advance/shift
Note on F183: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE SUB-LEVEL
Note on F108: Length to be mined after the initial cut of the sub-level
Note on I111: Evaluation of the number of blasts required for the construction of the infrastructure
Note on H105: Dimensions of the required opening for the construction of the infrastructure
Note on B116: Time required to scale one meter (the roof and the two walls) and to clean the bootlegs
Note on B141: see sheet " MUCKING "
Note on E141: see "Mucking" sheet
Note on F221: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE SUB-LEVEL
2
1
PLAN VIEW
3
4

## Mucking
Version: January 25, 2002
MUCKING
ENTER YOUR CHOICE IN CYCLE CALCULATIONS |  |  | tonnes/hour | equipment
|  |  | 46 | hoist |  | Table (entries, results)
[6 empty] | distance (m) | t/hour | m³/hour | availability | tonnes/hr
[5 empty] | HOIST 18.5 HP @ 90psi (Ingersoll-Rand) | 20 | 49 | 23.1371 | 95% | 46.55
[5 empty] | CAVO 310 | 50 | 36 | 16.6529 | 90% | 32.4
[5 empty] | ELECTRIC SCOOP EJC 60E | 80 | 39 | 18.0997 | 85% | 33.15
Broken ore density (t/m³) | 2.1377 |  |  |  | YOUR EQUIPMENT | 100 | 38 | 17.7859 | 85% | 32.3
HOIST 18.5 HP @ 90psi (Ingersoll-Rand)
distance (m) | t/hour | m³/hour | distance (ft) | sh.tons/hour
12.1951 | 68.9467 | 32 | 40 | 76
18.2927 | 53.5244 | 25 | 60 | 59
24.3902 | 42.6381 | 20 | 80 | 47
30.4878 | 36.2878 | 17 | 100 | 40
36.5854 | 30.8446 | 14 | 120 | 34
42.6829 | 27.2158 | 13 | 140 | 30
48.7805 | 25.4014 | 12 | 160 | 28
54.878 | 23.587 | 11 | 180 | 26
60.9756 | 19.0511 | 9 | 200 | 21
67.0732 | 18.1439 | 8 | 220 | 20
73.1707 | 16.3295 | 8 | 240 | 18
91.4634 | 12.7007 | 6 | 300 | 14
Enter your average operating distance
20 | 49 | 23.1371
CAVO 310
distance (m) | t/hour | m³/hour
10 | 52 | 24.2
25 | 43 | 20
50 | 35 | 16.3
75 | 28 | 13.3
100 | 24 | 11.2
Enter your average operating distance
50 | 36 | 16.6529
ELECTRIC SCOOP EJC 60E
distance (m) | t/hour | m³/hour
10 | 53 | 25
25 | 47 | 22
50 | 43 | 20
75 | 38 | 18
100 | 34 | 16
125 | 32 | 15
150 | 30 | 14
175 | 28 | 13
Enter your average operating distance
80 | 39 | 18.0997
YOUR EQUIPMENT
distance (m) | t/hour | m³/hour
10 | 56 | 26
25 | 49 | 23
50 | 45 | 21
75 | 41 | 19
100 | 36 | 17
125 | 34 | 16
150 | 32 | 15
175 | 30 | 14
Enter your average operating distance
100 | 38 | 17.7859
Note on A6: Methodology: 1- Enter the distance and availability per equipment. (It is possible to optimize the distance per equipment) 2- Enter the broken ore density. 3- Enter the chosen performance to use in the model.
Note on H5: Enter the average mucking distance according to your stope configuration
Note on K5: Availability observed at your site or from your references
Note on C73: Modify the formula according to the one in the graph

## Drawing
2
1
PLAN VIEW
3
4