## Stope
Shrinkage Stope Evaluation
Version: December 18, 2002
1.0 - Physical parameters of the stope
Typical stope
|  | Vertical height (m) | [5 empty] | Swell
Length (m) | Width (m) |  | Dip (°) | Slope distance (m) |  |  | Density (t/m³) | factor
55 | 1.8 | 60 | 80 | 60.9256 |  |  | 2.9 | 1.38
Ore (reserves) |  | Milled ore
Tonnage | Grade (g/t) | Tonnage | Grade (g/t) | Dilution
17491.7388 | 17.4 | 19240.9127 | 15.9091 | 10%
2.0 - Stope development
2.1 - Development parameters
|  | Dimensions |  |  |  | M advanced /shift | M advanced /manshift
|  | Width | Height | T/m advanced | # of men
Drift 1 |  | 2.4 | 2.6 | 18.096 | 2 | 2.3 | 1.15
Drift 2 |  | 2.6 | 2.7 | 20.358 | 2 | 2.3 | 1.15
Drawpoints |  | 3 | 2.7 | 23.49 | 2 | 1.8 | 0.9
Timbered raise |  | 1.8 | 2.4 | 12.528 | 2 | 1.8 | 0.9
Alimak raise |  | 2.7 | 2.7 | 21.141 | 2 | 2.3 | 1.15
Open raise |  | 1.8 | 2.4 | 0 | 2 | 2.3 | 1.15
Sub-level 1 |  | 2.4 | 2.4 | 16.704 | 2 | 2.3 | 1.15
Sub-level 2 |  | 2.4 | 3 | 20.88 | 2 | 1.8 | 0.9
2.2 - Required development (see "Development" sheet)
BY THE UPPER | Ore |  |  |  | Waste |  | Total
LEVEL | Length | Tonnes/meter | Dilution | Diluted grade (g/t) | Length | Tonnes/meter | Length | Tonnes
Upper drifts | 60 | 21.1 | 35% | 5 | 70 | 21.1 | 130 | 2743
Stope access | [6 empty] | 0 | 0
[7 empty] | 0 | 0
TOTAL | 60 | 21.1 |  | 5 | 70 | 21.1 | 130 | 2743
BY THE LOWER | Ore |  |  |  | Waste |  | Total
LEVEL | Length | Tonnes/meter | Dilution | Diluted grade (g/t) | Length | Tonnes/meter | Length | Tonnes
Lower drifts |  |  |  |  | 70 | 21.1 | 70 | 1477
Drawpoints |  |  |  |  | 60 | 23.5 | 60 | 1410
Raise | 61 | 10.6 | 30% | 16 |  |  | 61 | 647
Openings for Alimak | [6 empty] | 0 | 0
Sub-level 1 | [6 empty] | 0 | 0
Sub-level 2
Sub-level 3
Stope access | [6 empty] | 0 | 0
[7 empty] | 0 | 0
TOTAL | 61 | 10.6 |  | 16 | 130 | 22.2077 | 191 | 3534
2.3 - Development schedule parameters
Number of shifts/day |  |  | 2 | shifts
Number of working days/month |  |  | 20.8 | working days
Contingency |  |  | 12%
2.0 - Stope development (cont'd)
2.4 - Calculation of the development time
Number of
Upper level |  | Length | # of shifts/day | Advances/shift | # required days | installation days | Total | Sequence |  |  | 1 | 2 | 3
Upper drifts |  | 130 | 2 | 2.3 | 29 | 2 | 31 | 2 | 2 | 31 | 0 | 31 | 0
Stope access |  | 0 |  |  | 0 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
[7 empty] | working days |  |  |  | 0 | 31 | 0
31
Number of
Lower level |  | Length | # of shifts/day | Advances/shift | # required days | installation days | Total | Sequence |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Lower drifts |  | 70 | 2 | 2.3 | 16 | 2 | 18 | 1 | 1 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0
Drawpoints |  | 60 | 2 | 1.8 | 17 | 1 | 18 | 2 | 2 | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0
Raise |  | 61 | 2 | 0.9 | 34 | 2 | 36 | 2 | 2 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0
Openings for Alimak |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 1 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 2 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 3 |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stope access |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | working days |  |  |  | 18 | 36 | 0 | 0 | 0 | 0 | 0
54
|  |  | Time + | Contingency = | TOTAL |  | DEVELOPMENT TIME
Lower level |  |  | 54 | 6.48 | 60.48 | working days | (WORKING DAYS)
Upper level |  |  | 31 | 3.72 | 34.72 | working days | 61
3.0 - Stope production calculation
3.1 - Mining parameters
Productivity |  |  | 30 | tonnes/manshift
Number of men/shift |  |  | 2 | men
Number of shifts/day |  |  | 2 | shifts
Number of working days/month |  |  | 20.8333 | working days
Milling days/year |  |  | 365 | working days
3.2 - Stope life calculation
Broken tonnes/day (in production) |  |  | 120 | tonnes | Stope life (production)
Mucked tonnes/day (in production) |  |  | 45.6 | tonnes | 146 | working days | 7.008 | months
Remaining tonnage inside the stope |  |  | 12583.3127 | tonnes
- Lost ore between drawpoints |  |  | 270 | tonnes
= Recovered tonnage inside the stope |  |  | 12313.3127 | tonnes | Time required to muck the rest of the stope
Tonnes/shift (final mucking of the stope) |  |  | 300 | tonnes/shift | 21 | working days | 1.008 | months
3.3 - Calculation of production with relation to the number of active stopes
In order to maintain a constant production rate, the number of production stopes must be proportional to the number of stopes in the final mucking phase.
Assuming that all stopes have the same configuration, the production time of 146 days divided by the final mucking time of 21 days will allow you to calculate
an optimum ratio of the production time over the final mucking time which is equal to |  |  |  |  | 6.95 | to maintain a maximum productivity with
a minimum number of active stopes.
Which means that the production will be optimal if 6.95 stopes are active for each stope in the final mucking phase.
|  |  |  | Actual tonnage/day |  |  | Average milled tonnage/day (annual basis)
Number of stopes (production phase) |  |  | 12 | 547 |  |  | 375
Number of stopes (final mucking phase) |  |  | 1.7266 | 1036 |  |  | 710
|  |  |  | 1583 |  |  | 1085
Note: The calculations presume that the work schedule is the same for production and ore mucking.
3.3.1 - Calculation of the number of stopes in the development phase to maintain the production rate
In order to maintain a constant production rate, the number of production stopes must be proportional to the number of stopes in the development phase.
Assuming that all stopes have the same configuration, the production time of 146 days divided by the development time of 61 days will allow you to calculate
an optimum ratio of the production time over the development time which is equal to |  |  |  |  | 2.39 | . |  | .
Which means that the production will be optimal if 2.39 stopes are active for each stope in the development phase.
Average milled ore tonnage/day (annual basis)
Number of stopes (production phase) |  |  | 12 | Actual ore tonnage/day
Number of stopes (development phase) |  |  | 5.0209 | 157 |  |  | 108
Note: The calculations presume that the work schedule is the same for production and development.
4.0 - Backfilling
4.1 - Calculation of the volume to backfill
Tonnes
Mined tonnage from the stope (dilution included) |  |  |  | 18473.5281
| Length | Width | Height | Tonnes
Drifts | 70 | 2.6 | 2.7 | 1425.06
Drawpoints | 50 | 3 | 2.7 | 1174.5
Others |  |  |  | 0
|  |  | Total tonnage | 21073.0881 |  | Volume to backfill | 7266.5821 | m³
4.2 - Calculation of the time required to backfill
|  |  | Number of barricades |  | Number of days/barricade |  | Working days
- Construction of barricades |  |  | 8 |  | 5 |  | 40
- Backfilling time |  | Backfilling capacity (solid tonnes/hour) |  |  | 125 | tonnes/hour
|  | In situ backfill density |  |  | 1.943 | tonnes/m³
|  | Effective backfilling time per shift |  |  | 6.5 | effective hours/shift
|  | Number of required shifts |  |  | 17.3772 | shifts | Working days
|  | Number of shifts/day |  |  | 2 | shifts/day | 8.6886
- Total time required |  | 48.6886 | working days
or
|  | 2.3408 | months | (in accordance with the development schedule entered in section 2.3)
5.0 - Compilation
DEVELOPMENT
|  | Waste |  | Ore |  |  | TOTAL
|  | Length (m) | Tonnes | Length (m) | Tonnes | Grade (g/t) | Length (m) | Tonnes
Drifts |  | 140 | 1477 | 60 | 1266 | 5 | 200 | 2743
Drawpoints |  | 60 | 1410 | 0 | 0 | 0 | 60 | 1410
Raises |  | 0 | 0 | 61 | 647 | 16 | 61 | 647
Sub-level 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-level 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other openings |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 200 | 2887 | 121 | 1913 | 8.72 | 321 | 4800
[6 empty] | 496 | ounces
MINED ORE CALCULATION FROM ORIGINAL RESERVES DURING STOPE DEVELOPMENT
|  | Diluted ore (Dev.) |  | Ore from reserves |  | Waste
|  | Tonnes | Grade (g/t) | Tonnes | Grade (g/t) | Tonnes
Raises |  | 646.6 | 16 | 497.3846 | 20.8 | 149.2154
Openings for Alimak |  | 0 | 0 | 0 | 0 | 0
Sub-level 1 |  | 0 | 0 | 0 | 0 | 0
Sub-level 2 |  | 0 | 0 | 0 | 0 | 0
Sub-level 3 |  | 0 | 0 | 0 | 0 | 0
|  | 646.6 | 16 | 497.3846 | 20.8 | 149.2154
[5 empty] | 308 | ounces
STOPE
[5 empty] | Tonnes | Grade (g/t)
Length | 55 | meters | Reserves |  | 16994.3542 | 15.9091
Width | 1.8 | meters | Dilution |  | 10%
Vertical height | 60 | meters | Lost ore between DP |  | 270 | 15.9091
Dip | 80 | ° | Mill recovery |  |  | 95.5%
Density | 2.9 | tonnes/m³
[5 empty] | Tonnes | Grade (g/t) | Ounces
|  |  | Milled ore * |  | 18473.5281 | 14.0753 | 7735
* The milled ore from the stope originates from the diluted geological reserves (section 1.0) minus the portion of the mined reserves
during stope development.
DEVELOPMENT + STOPE
[5 empty] | Tonnes | Grade (g/t) | Ounces
|  |  |  | Milled ore from development | 1913 | 8.72 | 496
|  |  |  | Milled ore from the stope | 18473.5281 | 14.0753 | 7735
[5 empty] | 20386.5281 | 13.5724 | 8231
Note on B8: Measured perpendicularly to the vein
Note on C9: Height of the stope to be mined, including the sub-level
Note on C118: See "Development" sheet to determine the lost tonnage
Note on D65: This percentage increases the development time (see cells E96 and E97)
Note on D105: See "Productivity_Shrinkage Stope" file if you wish to verify the productivity for your operation
Note on D132: Enter the number of active stopes in relation to the desired production level
Note on E13: Extra dilution to the one already included in the geological reserves. See "Stope_Dilution" file if you wish to verify your estimate.
Note on I71: Identify the critical path by entering different figures
Note on I81: Identify the critical path by entering different figures
H ver
D°

## Development
Version: December 18, 2002
Drawpoint parameters
Physical parameters
|  |  |  | Vertical height (m) |  | Density (t/m³) | Swell
- Typical stope |  | Length (m) | Width (m) |  | Dip (°) |  | factor
|  | 55 | 1.8 | 60 | 80 | 2.9 | 1.38
- Drawpoint parameters
Friction angle
Planned spacing (m) |  | Drawpoint width (m) |  | Length (m) | of the ore (°)
10 |  | 2.9 |  | 10 | 38
Drawpoints at both ends |  |  | No drawpoint at both ends |  |  | One drawpoint at one end
Number | Actual spacing |  | Number | Actual spacing |  | Number | Actual spacing
6 | 11 | meters | 5 | 11 | meters | 6 | 10 | meters
Lost ore between drawpoints |  |  | Lost ore between drawpoints |  |  | Lost ore between drawpoints
Height (m) | Volume (m³) | Tonnes | Height (m) | Volume (m³) | Tonnes | Height (m) | Volume (m³) | Tonnes
3.1642 | 126.8689 | 266.6085 | 3.1642 | 103.8018 | 218.1342 | 2.7736 | 97.4769 | 204.8428
Raise configurations depending on its position in relation to the stope
Central raise in the ore
Vertical difference (m) |  | Dip (°) | Length (m) | Horizontal distance (m)
60 |  | 80 | 60.9256 | 10.5796
Central raise in the waste in a wall with regularly spaced sub-levels
RAISE
|  |  | Vertical difference (m) |  | Dip (°) | Density (t/m³) | T/m avanced | Raise length
|  |  | 60 |  | 80 | 2.9 | 10.6 | 60.9256
SUB-LEVELS
|  |  | Sub-level height | Sub-level width | Sub-level length | T/sub-level
|  |  | 2.4 | 1.8 | 6.8598 | 86
|  |  | Number of sub-levels |  | Actual spacing between sub-levels (m)
|  |  | 4 |  | 10.08
|  |  | Thickness of pillar between the raise and the stope |  |  | 6.7555 | meters
|  |  | Compilation | Sub-levels | Raise | TOTAL
|  |  | Length (m) | 10.8598 | 60.9256 | 71.7854
|  |  | Tonnes | 344 | 646 | 990
Cross-section
Raise in the ore at one end with sub-levels
RAISE
|  |  | Vertical difference (m) |  | Dip (°) | Density (t/m³) | T/m avanced | Raise length | Grade (g/t)
|  |  | 60 |  | 80 | 2.9 | 12.4 | 60.9256 | 10
SUB-LEVELS
|  |  | Sub-level height | Sub-level width | Sub-level length | T/sub-level | Grade (g/t)
|  |  | 2.4 | 1.8 | 6.8598 | 86 | 10
|  |  | Number of sub-levels |  | Actual spacing between sub-levels (m)
|  |  | 4 |  | 10.08
|  |  | Thickness of pillar between the raise and the stope |  |  | 6.8598 | meters
|  |  | Compilation | Sub-levels | Raise | TOTAL
|  |  | Length (m) | 10.8598 | 60.9256 | 71.7854
Longitudinal view |  |  | Tonnes | 344 | 755 | 1099
|  |  | Grade (g/t) | 10 | 10 | 10
Note on C14: If the drawpoint is still filled with ore, you must enter "0" in the drawpoint width
Spacing
Spacing
Spacing

## Drawings
Version: December 18, 2002
Part A
Part B
RAISE
1
3
4
2
Typical mining steps by Breasts
RAISE
3
4
2
1
5
6
7
8
9
10
11
level of broken ore before step 1
Raise outside the stope
(Breasts)
Part A
Part B
RAISE
1
3
4
2
1
5
Typical mining steps by Uppers
RAISE
1
level of broken ore before step 1
Central raise
(Breasts)
1
2
2
approximately 50 m in length