## UPPERS
CUT AND FILL
LIFT BY UPPERS | [8 empty] | Version: May 11, 2004
1.0 - DIRECT FIXED ACTIVITIES PER SHIFT (outside the stope)
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  | NOTES
Cage (at beginning and end of shift) |  | 2 | 10 | 20
Travelling (shaft - refuge station - shaft) |  | 2 | 5 | 10
Other travelling delays |  |  |  | 0
Back and forth to stope |  | 4 | 10 | 40
Supervision |  | 1 | 15 | 15
Work planning |  | 1 | 10 | 10
Complete daily reports |  | 1 | 12 | 12
Lunch |  | 1 | 30 | 30
0
|  |  |  | 137 | minutes
|  |  |  | 2.2833 | hours/shift
2.0 - DIRECT FIXED ACTIVITIES PER STEP (inside the stope)
RELATED TO GROUND |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | RELATED TO |  | Frequency or Units | Time (min)/Unit | Total Time (min)
SUPPORT | [5 empty] | BLASTING
Bring equipment and material |  | 1 | 15 | 15 |  | Bring explosives |  | 1 | 5 | 5
Install setup platform |  |  |  | 0 |  | Bring and prepare material |  | 1 | 6 | 6
Store material |  | 1 | 5 | 5 |  | Store equipment and explosives |  | 1 | 5 | 5
|  |  |  | 0 |  | Remove setup platform |  |  |  | 0
|  |  | minutes/setup | 20 |  | Equipment checks |  | 1 | 10 | 10
|  |  | hours/setup | 0.33333 |  | Connect the blast |  | 1 | 8 | 8
[6 empty] | Access verification |  | 1 | 5 | 5
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | Extra scaling |  | 1 | 5 | 5
RELATED TO DRILLING | [5 empty] | Repair and install ventilation |  | 1 | 15 | 15
Prepare material |  | 1 | 5 | 5 | [5 empty] | 0
Store equipment and material |  | 1 | 5 | 5 | [5 empty] | 0
|  |  |  | 0 |  |  |  |  | minutes/blast | 59
|  |  | minutes/setup | 10 |  |  |  |  | hours/blast | 0.98333
|  |  | hours/setup | 0.16667
3.0 - DIRECT FIXED ACTIVITIES PER LIFT (inside the stope)
RELATED TO BACKFILL,
MILL HOLES AND MANWAYS |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | OTHER ACTIVITIES |  | Frequency or Units | Time (min)/Unit | Total Time (min)
PER LIFT
Drainage system* |  | 2 | 30 | 60 |  | Geologists |  | 2 | 20 | 40
Mill holes * |  | 3 | 360 | 1080 |  | Surveyors |  | 2 | 30 | 60
Manways * |  | 3 | 360 | 1080 |  | Mechanics and electricians |  | 1 | 30 | 30
Barricades inside the stope * |  | 3 | 360 | 1080 |  | Repairs in main access |  | 2 | 20 | 20
Move equipment prior to backfill |  | 2 | 300 | 600 | [5 empty] | 0
Install backfill line inside the stope |  | 2 | 180 | 360 | [5 empty] | 0
Connect to the main line |  | 2 | 20 | 40 |  |  |  |  | minutes | 150
Wash the line before backfilling |  | 6 | 7 | 42 |  |  |  |  | hours | 2.5
Wash the line after backfilling |  | 6 | 12 | 72
Spill fences (outside the stope) |  | 2 | 15 | 30
0
|  |  |  | 4444 | minutes
* must include material handling and construction |  |  |  | 74.0667 | hours (backfill)
Here are the most common steps
in Cut and Fill:
The two slot raises at either end of the stope are optional. If you would
rather use the main raise as a slot, just enter "0" in the "Number of
rounds per lift" cell in the "Slot raise parameters" section.
4.0 - DIRECT VARIABLE ACTIVITIES PER STEP (inside the stope)
4.1 - Lift Dimensions
| Slot raise |  |  | Lift
| parameters |  |  | parameters
Number of rounds/lift | 3 |  |  | Length | 99.6
Drilled length/round | 2.4 |  |  | Average width | 1.7 |  | ore density (t/m³)
Broken length/round | 2.2 |  |  | Height | 2.2 |  | 2.95
Total tonnes in rounds | 80 |  |  | Tonnes | 1099
4.2 - Scaling |  |  |  |  | total hours (lift )
| minutes/ |  |  | minutes/
| longitudinal m | hours |  | longitudinal m
Wash, scale and clean bootlegs | 15 | 0.6 |  | 15 | 24.9
GROUND SUPPORT PARAMETERS
4.3 - Ground Support | [7 empty] | Drilled length/bolt | Number of bolts/1.2 m advanced | Drilled meters/m avanced
|  | hours |  |  | hours
Drilling for support |  | 2.2 |  |  | 32 | Roof pattern |  | 1.2 | 3 | 3.1
| installation time /bolt (min) |  |  |  |  | Hanging wall pattern |  | 1.2 | 2 | 2.1
|  | hours |  |  | hours | Footwall pattern |  | 1.2 | 2 | 2.1
Installation of ground support | 8.5 | 6.6 |  |  | 98.8 |  |  |  | 7 | 7.3
(screen included) |  | total hours |  |  | total hours
|  | 8.8 |  |  | 130.8
FINAL FLOOR CLEAN-UP PARAMETERS
4.4 - Mucking or Scraping | [6 empty] | Surface to clean (m2)
| tonnes/hour | hours |  | tonnes/hour | hours |  | Rounds | Lift | TOTAL | Aver. thickness (m)
Mucking | 50 | 1.6 |  | 53 | 20.8 |  | 12.24 | 169.32 | 181.56 | 0.15
Recovered tonnage
| m2/hour | hours |  | m2/hour | hours |  | Rounds | Lift | TOTAL
Final clean-up before backfill | 15 | 0.9 |  | 20 | 8.5 |  | 4.012 | 55.4993 | 59.5113
4.5 - Drilling | [5 empty] | DRILLING PARAMETERS
[6 empty] | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
[6 empty] | Time required for repositioning, changing drilling steel and bits, etc per hole of 2.4 m (min) |  |  |  | 2
| drilled holes/round | meters |  | # holes | meters | Total average time to drill a 2.4-m hole (min) |  |  |  | 6.32
Meters to drill | 31 | 223.2 |  | 498 | 1195.2
|  | hours |  |  | hours | Average drilling rate |  |  |  | 22.7848
Time required for drilling (hours) |  | 9.796 |  |  | 52.456 | (drilled meters per hour/man/drill)
| 80 | tonnes |  | 1099 | tonnes | DRILLING PATTERN (uppers)
[6 empty] | Drilled length (m) | Broken length (m) | Average width (m)
Burden (m)
[6 empty] | 2.4 | 2.2 | 1.7 | 0.6
[7 empty] | Number of rows | Number of holes/row
[7 empty] | 166 | 3
[6 empty] | t/drilled m | 0.91951 | tonnes per hole |  | 2.2068
4.6 - Loading and Blasting | [5 empty] | BLASTING PARAMETERS
| average time/ hole (min) |  |  | average time/ hole (min) | total hours (lift) |  | Hole diameter (mm) | 32
|  | hours |  |  |  |  | Explosive density (g/cc) | 1.01
Clean and load holes | 0.7 | 0.98 |  | 0.7 | 13.944 |  |  |  | Powder factor (kg/tonne)
[6 empty] | Kg of explosives/meter |  | 0.81229 | 0.80978
| holes/blast | number of blasts |  | holes/blast | length (m)/blast
Blasting | 28 | 3 |  | 42 | 8.4 |  | Number of blasts (lift) |  |  | 12
Required explosives (kg) |  | 55 |  |  | 890
4.7 - Ventilation
(To use when blasting causes a delay during the shift or when the work schedule is 24 hours a day)
Ventilation | Total number of blasts (rounds + lift) |  |  | minutes required
(evacuation of fumes) | 15 |  |  | /blast | total hours
|  |  |  | 0 | 0
4.8 - Backfill
| m³ | µ =t/m³ | t/hour | hours
| 399.661 | 1.9765 | 110 | 7.2 | for the entire lift
MILLHOLES, MANWAYS, BACKFILL
5.0 - LIFT COMPILATION
TABLE OF REQUIRED HOURS PER LIFT
DIRECT ACTIVITIES PER LIFT
(inside the stope) |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION |  | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 5 | 2.5 | 3.75 | 14.75 | 0 | 74.0667 | 2.5 | 102.5667
DIRECT VARIABLE (hours) |  | 25.5 | 139.6 | 62.252 | 31.8 | 14.924 |  | 7.2 |  | 281.276
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 12.75 | 69.8 | 31.126 | 31.8 | 7.462 |  | 7.2 |  | 160.138
* The number of required hours is corrected according to the number of men entered in section 5.0.
REQUIRED MANHOURS |  | 25.5 | 149.6 | 67.252 | 71.1 | 44.424 | 0 | 162.5333 | 5 | 525.4093 | manhours
REQUIRED MANSHIFTS |  | 3.1875 | 18.7 | 8.4065 | 8.8875 | 5.553 | 0 | 20.3167 | 0.625 | 65.6762 | manshifts
+
REQUIRED NUMBER OF MEN |  | 2 |  |  |  | with a contingency of | 15% |  | manshift contingency | 9.8514
NUMBER OF HOURS PER SHIFT |  | 8 | hours | [6 empty] | =
[9 empty] | required manshifts inside the stope | 75.5276
+
[9 empty] | required manshifts from direct fixed activities (outside the stope) | 30.167
=
[9 empty] | total manshifts required | 105.6946
MANSHIFTS
| INSIDE THE STOPE |  |  |  | OUTSIDE STOPE | TOTAL |  |  | 1179 | tonnes
| PRODUCTIVE | CONTINGENCY | TOTAL (STOPE) |  | FIXED
| 65.6762 | 9.8514 | 75.5276 |  | 30.167 | 105.6946 | PRODUCTIVITY |  | 11.1548 | tonnes/manshift
| 62.14% | 9.321% | 71.46% |  | 28.54% | 100%
Note on B89: Time necessary to advance one meter inculding the back and the two walls and cleaning the bootlegs.
Note on B104: see "MUCKING" sheet
Note on B107: If the grade does not justify the time required for the final clean-up, enter "0" in the "m2/hour" cell
Note on E89: Time required to scale one meter (the roof and the two walls) and to clean the bootlegs
Note on E104: see sheet " MUCKING "
Note on E107: If the grade does not justify the time required for the final clean-up, enter "0" in the "m2/hour" cell
Note on E134: The number of holes per blast must be a multiple of the "Number of holes per row" cell of the "Drilling pattern" section
Note on F81: Length to be mined without the slot raises and the main raise
Note on F164: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE STOPE
Note on I164: NOT PROPORTIONAL TO THE NUMBER OF MEN IN THE STOPE
Note on J121: Distance between rows
RAISE
BACKFILL
1
3
4
2
1
5
FENCE
part A
part B

## BREASTS
CUT AND FILL
LIFT BY BREASTS
Version: May 11, 2004
1.0 - DIRECT FIXED ACTIVITIES PER SHIFT (outside the stope)
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  | NOTES
Cage (at beginning and end of shift) |  | 2 | 10 | 20
Travelling (shaft - refuge station - shaft) |  | 2 | 5 | 10
Other travelling delays |  |  |  | 0
Back and forth to stope |  | 4 | 10 | 40
Supervision |  | 1 | 15 | 15
Work planning |  | 1 | 10 | 10
Complete daily reports |  | 1 | 12 | 12
Lunch |  | 1 | 30 | 30
0
|  |  |  | 137 | minutes
|  |  |  | 2.2833 | hours/shift
2.0 - DIRECT FIXED ACTIVITIES PER STEP (inside the stope)
RELATED TO GROUND |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | RELATED TO |  | Frequency or Units | Time (min)/Unit | Total Time (min)
SUPPORT | [5 empty] | BLASTING
Bring equipment and material |  | 1 | 10 | 10 |  | Bring explosives |  | 1 | 5 | 5
Install setup platform |  |  |  | 0 |  | Bring and prepare material |  | 1 | 6 | 6
Store material |  | 1 | 5 | 5 |  | Store equipment and explosives |  | 1 | 8 | 8
|  |  |  | 0 |  | Remove setup platform |  | 1 | 5 | 5
|  |  | minutes/setup | 15 |  | Equipment checks |  |  |  | 0
|  |  | hours/setup | 0.25 |  | Connect the blast |  | 1 | 10 | 10
[6 empty] | Access verification |  | 1 | 5 | 5
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | Extra scaling |  | 1 | 5 | 5
RELATED TO DRILLING | [5 empty] | Repair and install ventilation |  | 1 | 15 | 15
Prepare material |  | 1 | 5 | 5 | [5 empty] | 0
Store equipment and material |  | 1 | 5 | 5 | [5 empty] | 0
|  |  |  | 0 |  |  |  |  | minutes/blast | 59
|  |  | minutes/setup | 10 |  |  |  |  | hours/blast | 0.98333
|  |  | hours/setup | 0.16667
3.0 - DIRECT FIXED ACTIVITIES PER LIFT (inside the stope)
RELATED TO BACKFILL,
MILL HOLES AND MANWAYS |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | OTHER ACTIVITIES |  | Frequency or Units | Time (min)/Unit | Total Time (min)
PER LIFT
Drainage system* |  | 2 | 30 | 60 |  | Geologists |  | 2 | 20 | 40
Mill holes * |  | 3 | 360 | 1080 |  | Surveyors |  | 1 | 30 | 30
Manways * |  | 3 | 360 | 1080 |  | Mechanics and electricians |  | 1 | 30 | 30
Barricades inside the stope * |  | 3 | 360 | 1080 |  | Repairs in main access |  | 1 | 10 | 10
Move equipment prior to backfill |  | 2 | 300 | 600 | [5 empty] | 0
Install backfill line inside the stope |  | 2 | 180 | 360 | [5 empty] | 0
Connect to the main line |  | 2 | 20 | 40 |  |  |  |  | minutes | 110
Wash the line before backfilling |  | 6 | 7 | 42 |  |  |  |  | hours | 1.8333
Wash the line after backfilling |  | 6 | 12 | 72
Spill fences (outside the stope) |  | 2 | 15 | 30
0
|  |  |  | 4444 | minutes
* must include material handling and construction |  |  |  | 74.0667 | hours (backfill)
Here are the most common steps
in Cut and Fill:
4.0 - DIRECT VARIABLE ACTIVITIES PER STEP (inside the stope)
4.1 - Lift Dimensions
| Breast |  |  | Lift
| parameters |  |  | parameters |  |  | ore density (t/m³)
2.95
| Drilled length | 3.05 |  | Length | 99.6
| Broken length | 3 |  | Height | 2.4
| Height | 2.4 |  | Average width | 1.7
| Width | 1.7 |  | # advances | 33
| Tonnes/breast | 37 |  | Tonnes | 1199
4.2 - Scaling
| minutes/ |  |  |  | total hours (lift)
| longitudinal m | hours
Wash, scale and clean bootlegs | 15 | 0.8 |  |  | 24.9
4.3 - Ground Support | [5 empty] | GROUND SUPPORT PARAMETERS
[8 empty] | Drilled length/bolt | Number of bolts/1.2 m advanced | Drilled meters/m avanced
|  | hours |  |  | hours
Drilling for support |  | 0.9 |  |  | 29.7 | Roof pattern |  | 1.2 | 2 | 2.1
| installation time /bolt (min) |  |  |  |  | Hanging wall pattern |  | 1.2 | 2 | 2.1
|  | hours |  |  | hours | Footwall pattern |  | 1.2 | 2 | 2.1
Installation of ground support | 8.5 | 2.6 |  |  | 85.8 |  |  |  | 6 | 6.3
(screen included) |  | total hours |  |  | total hours
|  | 3.5 |  |  | 115.5
FINAL FLOOR CLEAN-UP PARAMETERS
4.4 - Mucking or Scraping | [6 empty] | Surface to clean (m2)
| tonnes/hour | hours |  | tonnes/hour | hours |  | LIFT TOTAL |  | Aver. thickness (m)
Mucking | 50 | 0.8 |  | 50 | 24 |  | 169.32 |  | 0.15
Recovered tonnage
| m2/hour | hours |  | m2/hour | hours |  | for the lift
Final clean-up before backfill | 15 | 0.4 |  | 15 | 11.3 |  | 49.4499
4.5 - Drilling | [5 empty] | DRILLING PARAMETERS
[6 empty] | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
[6 empty] | Time required for repositioning, changing drilling steel and bits, etc. per hole of 2.4 m (min) |  |  |  | 2
[6 empty] | Total average time to drill a 2.4-m hole (min) |  |  |  | 6.32
|  | meters |  |  | meters | Average drilling rate |  |  |  | 22.7848
Meters to drill |  | 27.45 |  |  | 905.85 | (drilled meters per hour/man/drill)
|  | hours |  |  | hours | DRILLING PATTERN (breasts)
Time required for drilling (hours) |  | 1.3 |  |  | 39.8 | Number of holes/breast |  |  | 9
[7 empty] | tonnes/drilled m | tonnes per hole
[7 empty] | 1.3479 | 4.1111
BLASTING PARAMETERS
4.6 - Loading and Blasting | [6 empty] | Hole diameter (mm) | 32 | Powder factor per breast (kg/tonne)
| average time/ hole (min) |  |  |  | total hours (lift) |  | Explosive density (g/cc) | 1.01
hours
Clean and load holes | 1.3 | 0.2 |  |  | 6.6 | Kg of explosives/meter |  | 0.81229 | 0.59275
Required explosives (kg) |  | 22 |  |  | 711 |  | Number of blasts (lift) |  |  | 33
4.7 - Ventilation
(To use when blasting causes a delay during the shift or when the work schedule is 24 hours a day)
minutes required
Ventilation | /blast |  |  |  | total hours
(evacuation of fumes) | 0 |  |  |  | 0
4.8 - Backfill
| m³ | µ =t/m³ | t/hour | hours
| 406.368 | 1.947 | 110 | 7.2 | for the entire lift
5.0 - BREAST COMPILATION
TABLE OF REQUIRED HOURS PER BREAST
DIRECT ACTIVITIES
PER ADVANCE |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 0.25 | 0.16667 | 0.25 | 0.73333 | 0 | 0.050505 | 1.4505
DIRECT VARIABLE (hours) |  | 0.8 | 3.5 | 1.3 | 0.8 | 0.2 |  |  | 6.6
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 0.4 | 1.75 | 0.65 | 0.8 | 0.1 |  |  | 3.7
* The number of required hours is corrected according to the number of men entered in section 5.0. | [7 empty] | total : | 5.1505
+
[8 empty] | contingency (ventilation included) | 15%
[8 empty] | allocated time for contingency | 46.3545 | minutes
=
[8 empty] | total time required inside the stope (contingency included) | 6 | hours
+
[8 empty] | total time of direct fixed activities outside the stope | 2.2833 | hours
| REQUIRED NUMBER OF MEN | 2 | [6 empty] | =
| NUMBER OF HOURS PER SHIFT | 8 | <=> |  |  |  |  | total time required per advance | 8.2833 | hours
[8 empty] | occupation rate of the stope per advance | 75%
[8 empty] | occupation rate of the shift per advance | 103.5%
5.1 - CALCULATION OF THE POSSIBLE NUMBER OF ADVANCES PER SHIFT ACCORDING TO ENTERED DATA:
In this section, you can optimize your operating parameters to simulate your operation or to find
the required parameters to reach the desired performance.
|  | Number of hours per shift | 8
-
|  | Direct fixed time outside the stope/shift | 2.2833 |  | total time required inside the stope (contingency included) |  |  | Possible number of advances per shift
=
|  | Available time inside the stope/shift | 5.7167 | / | 6 |  | = | 0.95278
Is it possible to blast during the shift? If no, change the parameters to obtain a round number
6.0 - LIFT COMPILATION | [7 empty] | MILLHOLES, MANWAYS, BACKFILL
DIRECT ACTIVITIES PER LIFT |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION |  | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 8.25 | 5.5 | 8.25 | 24.2 | 0 | 74.0667 | 1.8333 | 122.1
DIRECT VARIABLE (hours) |  | 24.9 | 115.5 | 39.8 | 35.3 | 6.6 |  | 7.2 |  | 229.3
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 12.45 | 57.75 | 19.9 | 35.3 | 3.3 |  | 7.2 |  | 135.9
* The number of required hours is corrected according to the number of men entered in section 5.0. | [8 empty] | total : | 258
total
REQUIRED MANHOURS |  | 24.9 | 132 | 50.8 | 87.1 | 55 | 0 | 162.5333 | 3.6667 | 516
REQUIRED MANSHIFTS |  | 3.1125 | 16.5 | 6.35 | 10.8875 | 6.875 | 0 | 20.3167 | 0.45833 | 64.5
+
REQUIRED NUMBER OF MEN |  | 2 |  |  |  | with a contingency of | 15% |  | manshift contingency | 9.675
NUMBER OF HOURS PER SHIFT |  | 8 | hours | [6 empty] | =
[9 empty] | required manshifts inside the stope | 74.175
+
[9 empty] | required manshifts from direct fixed activities (outside the stope) | 29.6267
=
[9 empty] | total manshifts required | 103.8017
[8 empty] | with a performance of | 0.95278 | advance/shift
|  |  |  | From your best estimate, you can maintain | 0.86 | advance/shift
|  |  |  | which represents an occupation rate of the shift (contingency included) of | 90.26%
MANSHIFTS
| INSIDE THE STOPE |  |  |  | OUTSIDE STOPE | TOTAL |  |  | 1199 | tonnes
| PRODUCTIVE | CONTINGENCY | TOTAL (STOPE) |  | FIXED
| 70.8287 | 10.6243 | 81.453 |  | 32.5337 | 113.9868 | PRODUCTIVITY |  | 10.5188 | tonnes/manshift
| 62.14% | 9.321% | 71.46% |  | 28.54% | 100%
Calculation of required manhifts with contingency |  |  | Calculation of number of shifts according to schedule |  |  |  | Calculation of number of shifts of direct fixed activities
Required manhours | 516 |  |  | Required manshifts with contingency | 74.175 |  |  | Number of required shifts (schedule) | 51.9009
| / |  |  |  | / |  |  |  | x
Hours/shift | 8 |  |  | Available hours inside the stope | 5.7167 |  |  | Direct fixed hours/shift | 2.2833
| = |  |  |  | x |  |  |  | /
Required manshifts | 64.5 |  |  | Hours/shift | 8 |  |  | Hours/shift | 8
| + |  |  |  | / |  |  |  | =
Contingency | 15% |  |  | Men | 2 |  |  | Number of shifts of direct fixed activities (schedule) | 14.8134
| = |  |  |  | =
Required manshifts | 74.175 |  |  | Number of required shifts (schedule) | 51.9009
with contingency
Calculation of total number of required manshifts
| Total number of required shifts | 51.9009
x
| Men | 2
=
| Required manshifts | 103.8017
| with a performance of | 0.95278 | advance/shift
Note on B97: Time required to scale one meter (the roof and the two walls) and to clean the bootlegs
Note on B114: see "MUCKING" sheet
Note on B117: If the grade does not justify the time required for the final clean-up, enter "0" in the "m2/hour" cell
Note on E114: see sheet " MUCKING "
Note on E117: If the grade does not justify the time required for the final clean-up, enter "0" in the "m2/hour" cell
Note on F89: Length to be mined without the main raise
Note on F167: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE STOPE
Note on F206: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE STOPE
Note on I206: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE STOPE
RAISE
BACKFILL
1
4
3
2
5 & 6
FENCE
part A
part B

## MUCKING
Version: April 13, 2004
MUCKING
ENTER YOUR CHOICE IN CYCLE CALCULATIONS |  |  | tonnes/ hour | equipment
|  |  | 46 | hoist |  | Table (entries, results)
[6 empty] | distance (m) | t/hour | m³/hour | availability | tonnes/hr
[5 empty] | HOIST 18.5 HP @ 90psi (Ingersoll-Rand) | 18 | 55 | 25.6123 | 95% | 52.25
[5 empty] | CAVO 310 | 50 | 36 | 16.6529 | 90% | 32.4
[5 empty] | ELECTRIC SCOOP EJC 60E | 80 | 39 | 18.0997 | 85% | 33.15
Broken ore density (t/m³) | 2.1377 |  |  |  | YOUR EQUIPMENT | 90 | 39 | 18.4378 | 85% | 33.15
HOIST 18.5 HP @ 90psi (Ingersoll-Rand)
distance (m) | t/hour | m³/hour | distance (ft) | sh.tons/hour
12.1951 | 68.9467 | 32 | 40 | 76
18.2927 | 53.5244 | 25 | 60 | 59
24.3902 | 42.6381 | 20 | 80 | 47
30.4878 | 36.2878 | 17 | 100 | 40
36.5854 | 30.8446 | 14 | 120 | 34
42.6829 | 27.2158 | 13 | 140 | 30
48.7805 | 25.4014 | 12 | 160 | 28
54.878 | 23.587 | 11 | 180 | 26
60.9756 | 19.0511 | 9 | 200 | 21
67.0732 | 18.1439 | 8 | 220 | 20
73.1707 | 16.3295 | 8 | 240 | 18
91.4634 | 12.7007 | 6 | 300 | 14
Enter your average operating distance
18 | 55 | 25.6123
CAVO 310
distance (m) | t/hour | m³/hour
10 | 52 | 24.2
25 | 43 | 20
50 | 35 | 16.3
75 | 28 | 13.3
100 | 24 | 11.2
Enter your average operating distance
50 | 36 | 16.6529
ELECTRIC SCOOP EJC 60E
distance (m) | t/hour | m³/hour
10 | 53 | 25
25 | 47 | 22
50 | 43 | 20
75 | 38 | 18
100 | 34 | 16
125 | 32 | 15
150 | 30 | 14
175 | 28 | 13
Enter your average operating distance
80 | 39 | 18.0997
YOUR EQUIPMENT
distance (m) | t/hour | m³/hour
10 | 56 | 26
25 | 49 | 23
50 | 45 | 21
75 | 41 | 19
100 | 36 | 17
125 | 34 | 16
150 | 32 | 15
175 | 30 | 14
Enter your average operating distance
90 | 39 | 18.4378
Note on A6: Methodology: 1- Enter the distance and availability per equipment. (It is possible to optimize the distance per equipment) 2- Enter the broken ore density. 3- Enter the chosen performance to use in the model.
Note on C73: Modify the formula according to the one in the graph
Note on H5: Enter the average mucking distance according to your stope configuration
Note on K5: Availability observed at your site or from your references

## BACKFILL
BACKFILL | [5 empty] | Version: April 13, 2004
BACKFILL PREPARATION | [5 empty] | Hours/shift | 8
| Surface of floor to clean (m²) | Cleaning productivity (m²/hour)
Actvities |  |  |  |  | Time (hours) | # men | Manshifts
Clean the floor | 450 | 20 |  |  | 22.5 | 2 | 5.625
| length (m) | productivity (m/hour)
Remove services | 110 | 20 |  |  | 5.5 | 2 | 1.375
| number of trips | productivity (#/hour)
Bring material | 56 | 4 |  |  | 14 | 2 | 3.5
Build mill holes and manways | number of parts | productivity (#/hour)
| 38 | 5 |  |  | 7.6 | 2 | 1.9
| number of parts | productivity (#/hour)
Build fences | 54 | 4 |  |  | 13.5 | 2 | 3.375
| length (m) | productivity (m/hour)
Install drainage | 20 | 30 |  |  | 0.66667 | 2 | 0.16667
Move equipment (with a fence) | number of parts | productivity (#/hour)
| 6 | 0.4 |  |  | 15 | 2 | 3.75
Move equipment (without a fence) | number of parts | productivity (#/hour)
| 6 | 0.9 |  |  | 6.6667 | 2 | 1.6667
Direct fixed time outside the stope per shift | [5 empty] | 2.45 | hours
(see section 1.0 of the "UPPERS" or "BREASTS" worksheets)
Manshifts
|  |  |  | with a fence |  | total | 29
|  |  |  | without a fence |  | total | 21
CONTINUOUS BACKFILLING | [5 empty] | hours/shift | 8
Activities | Time (hours) | # men | M-Sh |  | required volume (m³)
Fixed time outside the stope | 2.45 | 2 | 0.6125 |  |  | solid rate (m³/hour)
Connect to main line | 0.75 | 2 | 0.1875 |  | 400 | 55.8376
Call the backfill | 0.083333 | 2 | 0.020833
Backfilling | 7.1636 | 2 | 1.7909
Wash the line | 0.3 | 2 | 0.075
|  | total : | 2.6867 | manshifts
BACKFILLING PER SHIFT | [5 empty] | hours/shift | 8
required volume (m³)
Activities | Time (hours) |  |  |  |  | solid rate (m³/hour)
Fixed time outside the stope | 2.45 |  |  |  | 400 | 55.8376
Connect to main line | 0.75
Call the backfill | 0.083333 |  | m³/sh
Backfilling/shift | 4.4167 |  | 246.6159
Wash the line | 0.3
|  | # men |  |  |  |  | Manshifts
Number of required shifts | 1.622 | 2 |  |  |  | total | 3.2439
SUMMARY - TOTAL MANSHIFTS REQUIRED
BACKFILLING
BACKFILL PREPARATION | CONTINUOUS | PER SHIFT
WITH A FENCE | 31.6867 | 32.2439
WITHOUT A FENCE | 23.6867 | 24.2439
Note on A9: Remove pipes, hoses, electric cables, ventilation ducts
Note on A42: Total time between the call and the arrival of the backfill flow
Note on A56: Total time between the call and the arrival of the backfill flow

## DRAWINGS
Steps for breast mining with a fence
Steps for breast mining without a fence
Steps for upper mining with a fence
part A
part B
RAISE
BACKFILL
1
3
4
2
part A
part B
RAISE
BACKFILL
1
3
4
2
1
5
FENCE
RAISE
BACKFILL
1
4
3
2
FENCE
5 & 6
part A
part B