## UPPERS
SHRINKAGE STOPE
LIFT BY UPPERS
Version: May 7, 2004
1.0 - DIRECT FIXED ACTIVITIES PER SHIFT (outside the stope)
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  | NOTES
Cage (at beginning and end of shift) |  | 2 | 10 | 20
Travelling (shaft - refuge station - shaft) |  | 2 | 2 | 4 |  |  | RAISE OUTSIDE THE STOPE
Other travelling delays |  | 1 | 10 | 10
Back and forth to stope |  | 2 | 10 | 20 |  |  | LEVEL THE BROKEN ORE ONCE PER LIFT
Supervision |  | 1 | 15 | 15
Work planning |  | 1 | 10 | 10
Complete daily reports |  | 1 | 12 | 12
Lunch |  | 1 | 30 | 30
Others - access verification |  | 1 | 10 | 10
|  |  |  | 131 | minutes
|  |  |  | 2.1833 | hours/shift
2.0 - DIRECT FIXED ACTIVITIES PER STEP (inside the stope)
RELATED TO GROUND |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | RELATED TO |  | Frequency or Units | Time (min)/Unit | Total Time (min)
SUPPORT | [5 empty] | BLASTING
Bring equipment and material |  | 1 | 10 | 10 |  | Bring explosives |  | 1 | 5 | 5
Install setup platform |  |  |  | 0 |  | Bring and prepare material |  | 1 | 6 | 6
Store material |  | 1 | 5 | 5 |  | Store equipment and explosives |  | 1 | 5 | 5
|  |  |  | 0 |  | Remove setup platform |  |  |  | 0
|  |  | minutes/setup | 15 |  | Connect the blast |  | 1 | 8 | 8
|  |  | hours/setup | 0.25 |  | Access verification |  | 1 | 5 | 5
[6 empty] | Extra scaling |  | 1 | 5 | 5
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | Repair and install ventilation |  | 1 | 8 | 8
RELATED TO DRILLING | [5 empty] | Mucking delay before blasting |  |  |  | 0
Prepare material |  | 1 | 5 | 5 | [5 empty] | 0
Store equipment and material |  | 1 | 5 | 5 | [5 empty] | 0
|  |  |  | 0 |  |  |  |  | minutes/blast | 42
|  |  | minutes/setup | 10 |  |  |  |  | hours/blast | 0.7
|  |  | hours/setup | 0.16667
3.0 - DIRECT FIXED ACTIVITIES PER LIFT (inside the stope)
RELATED TO MANWAYS |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | OTHER ACTIVITIES |  | Frequency or Units | Time (min)/Unit | Total Time (min)
(see steps 4 & 5 in drawing) | [5 empty] | PER LIFT
Preparation to build manways |  | 1 | 20 | 20 |  | Geologists |  | 2 | 10 | 20
Bring material |  |  | 70 | 70 |  | Surveyors |  | 1 | 30 | 30
Build manways |  |  | 120 | 120 |  | Mechanics and electricians |  | 1 | 30 | 30
Store material |  |  | 30 | 30 |  | Level ore with scraper |  | 1 | 240 | 240
|  |  |  | 0 |  | Repairs in main access |  | 1 | 20 | 20
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 240 | minutes |  |  |  | minutes | 340
|  |  |  | 4 | hours (manways) |  |  |  | hours | 5.6667
Here are the most common steps
in Shrinkage Stopes:
The two slot raises at either end of the stope are optional. If you would
rather use the main raise as a slot, just enter "0" in the "Number of rounds
per lift" cell in the "Slot raise parameters" section.
4.0 - DIRECT VARIABLE ACTIVITIES PER STEP (inside the stope)
4.1 - Lift Dimensions
| Slot raise |  |  | Lift
| parameters |  |  | parameters
Number of rounds/lift | 2 |  |  | Length | 22.8
Drilled length/round | 2.4 |  |  | Average width | 1.7 |  | ore density (t/m³)
Broken length/round | 2.3 |  |  | Height | 2.3 |  | 2.95
Total tonnes in rounds | 56 |  |  | Tonnes | 263
4.2 - Scaling |  |  |  |  | total hours (lift)
| minutes/ |  |  | minutes/
| longitudinal m | hours |  | longitudinal m
Wash, scale and clean bootlegs | 15 | 0.6 |  | 15 | 5.7
GROUND SUPPORT PARAMETERS
4.3 - Ground Support | [7 empty] | Drilled length/bolt | Number of bolts/1.2 m advanced | Drilled meters/meter avanced
|  | hours |  |  | hours
Drilling for support |  | 1.5 |  |  | 7.2 | Roof pattern |  | 1.2 | 3 | 3.1
| installation time /bolt (min) |  |  |  |  | Hanging wall pattern |  | 1.2 | 2 | 2.1
|  | hours |  |  | hours | Footwall pattern |  | 1.2 | 2 | 2.1
Installation of ground support | 2.3 | 1.3 |  |  | 6.2 |  |  |  | 7 | 7.3
(screen included) |  | total hours |  |  | total hours
|  | 2.8 |  |  | 13.4
DRILLING PARAMETERS
4.4 - Drilling | [5 empty] | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
[6 empty] | Time required for repositioning, changing drilling steel and bits, etc. per hole of 2.4 m (min) |  |  |  | 1.85
drilled holes/round
|  | meters |  | # holes | meters | Total average time to drill a 2.4-m hole (min) |  |  |  | 6.17
Meters to drill | 31 | 148.8 |  | 152 | 364.8
|  | hours |  |  | hours | Average drilling rate |  |  |  | 23.3387
Time required for drilling (hours) |  | 6.3757 |  |  | 15.6307 | (drilled meters per hour/man/drill)
| 56 | tonnes |  | 263 | tonnes | DRILLING PATTERN (uppers)
[6 empty] | Drilled length (m) | Broken length (m) | Average width (m)
Burden (m)
[6 empty] | 2.4 | 2.3 | 1.7 | 0.6
[7 empty] | Number of rows | Number of holes/row
[7 empty] | 38 | 4
[6 empty] | tonnes/drilled m | 0.72094 | tonnes per hole |  | 1.7303
4.5 - Loading and Blasting | [5 empty] | BLASTING PARAMETERS
| average time/ hole (min) |  |  | average time/ hole (min) | total hours (lift) |  | Hole diameter (mm) | 32
|  | hours |  |  |  |  | Explosive density (g/cc) | 1.01
Clean and load holes | 0.7 | 0.65333 |  | 0.7 | 4.256 |  |  |  | Powder factor (kg/tonne)
[6 empty] | Kg of explosives/meter |  | 0.81229 | 1.0798
| holes/blast | number of blasts |  | holes/blast | length (m)/blast
Blasting | 28 | 2 |  | 30 | 4.5 |  | Number of blasts (lift) |  |  | 6
4.6 - Ventilation
(To use when blasting causes a delay during the shift or when the work schedule is 24 hours a day)
| Total number of blasts (rounds + lift) |  |  | minutes required
Ventilation | 8 |  |  | /blast | total hours
(evacuation of fumes) |  |  |  | 0 | 0
5.0 - LIFT COMPILATION
TABLE OF REQUIRED HOURS PER LIFT
DIRECT ACTIVITIES PER LIFT
(inside the stope) |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION | MANWAYS | OTHERS | Scheduled hours
DIRECT FIXED (hours) |  | see support | 2 | 1.3333 | 4 | 5.6 | 0 | 4 | 1.6667 | 18.6
DIRECT VARIABLE (hours) |  | 6.3 | 16.2 | 22.0063 |  | 4.9093 |  |  |  | 49.4157
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 3.15 | 8.1 | 11.0032 |  | 2.4547 |  |  |  | 24.7078
* The number of required hours is corrected according to the number of men entered in section 5.0.
REQUIRED MANHOURS |  | 6.3 | 20.2 | 24.673 | 8 | 16.1093 | 0 | 8 | 3.3333 | 86.6157 | manhours
REQUIRED MANSHIFTS |  | 0.7875 | 2.525 | 3.0841 | 1 | 2.0137 | 0 | 1 | 0.41667 | 10.827 | manshifts
+
REQUIRED NUMBER OF MEN |  | 2 |  |  |  | with a contingency of | 10% |  | manshift contingency | 1.0827
NUMBER OF HOURS PER SHIFT |  | 8 | hours | [6 empty] | =
[9 empty] | required manshifts inside the stope | 11.9097
+
[9 empty] | required manshifts from direct fixed activities (outside the stope) | 4.4704
=
[9 empty] | total manshifts required | 16.38
MANSHIFTS
| INSIDE THE STOPE |  |  |  | OUTSIDE STOPE | TOTAL |  |  | 319 | tonnes
| PRODUCTIVE | CONTINGENCY | TOTAL (STOPE) |  | FIXED
| 10.827 | 1.0827 | 11.9097 |  | 4.4704 | 16.38 | PRODUCTIVITY |  | 19.4749 | tonnes/manshift
| 66.1% | 6.61% | 72.71% |  | 27.29% | 100%
Note on B85: Time required to scale one meter (the roof and the two walls) and to clean the bootlegs
Note on F77: Length to be mined without the slot raises and the main raise
Note on I53: Enter the time required to level the broken ore for the entire lift when done in a single step (must include mucking delays)
Note on J108: Distance between rows
Part A
Part B
RAISE
1
3
4
2
1
5
Typical mining steps by Uppers

## BREASTS
SHRINKAGE STOPE
LIFT BY BREASTS
Version: May 7, 2004
1.0 - DIRECT FIXED ACTIVITIES PER SHIFT (outside the stope)
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  | NOTES
Cage (at beginning and end of shift) |  | 2 | 10 | 20
Travelling (shaft - refuge station - shaft) |  | 2 | 2 | 4 |  |  | RAISE OUTSIDE THE STOPE
Other travelling delays |  | 1 | 10 | 10
Back and forth to stope |  | 2 | 10 | 20 |  |  | LEVEL THE BROKEN ORE ONCE PER LIFT
Supervision |  | 1 | 15 | 15
Work planning |  | 1 | 10 | 10 |  |  | FOUR LIFTS ARE INCLUDED IN THE
Complete daily reports |  | 1 | 12 | 12 |  |  | CALCULATIONS
Lunch |  | 1 | 30 | 30
Others - access verification |  | 1 | 10 | 10
|  |  |  | 131 | minutes
|  |  |  | 2.1833 | hours/shift
2.0 - DIRECT FIXED ACTIVITIES PER STEP (inside the stope)
RELATED TO GROUND |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | RELATED TO |  |  | Frequency or Units | Time (min)/Unit | Total Time (min)
SUPPORT | [5 empty] | BLASTING
Bring equipment and material |  | 1 | 15 | 15 |  | Bring explosives |  |  | 1 | 5 | 5
Install setup platform |  |  |  | 0 |  | Bring and prepare material |  |  | 1 | 6 | 6
Store material |  | 1 | 5 | 5 |  | Store equipment and explosives |  |  | 1 | 5 | 5
|  |  |  | 0 |  | Remove setup platform |  |  |  |  | 0
|  |  | minutes/setup | 20 |  | Connect the blast |  |  | 1 | 8 | 8
|  |  | hours/setup | 0.33333 |  | Access verification |  |  | 1 | 5 | 5
[6 empty] | Extra scaling |  |  | 1 | 5 | 5
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | Repair and install ventilation |  |  | 1 | 2 | 2
RELATED TO DRILLING | [5 empty] | Mucking delay before blasting |  |  |  |  | 0
Prepare material |  | 1 | 5 | 5 | [6 empty] | 0
Store equipment and material |  | 1 | 5 | 5 | [6 empty] | 0
|  |  |  | 0 | [5 empty] | minutes/blast | 36
|  |  | minutes/setup | 10 | [5 empty] | hours/blast | 0.6
|  |  | hours/setup | 0.16667
3.0 - DIRECT FIXED ACTIVITIES PER LIFT (inside the stope)
RELATED TO MANWAYS |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | OTHER ACTIVITIES |  |  | Frequency or Units | Time (min)/Unit | Total Time (min)
(see steps 2 & 4 in drawing) | [5 empty] | PER LIFT
Preparation to build manways |  | 4 | 20 | 80 |  | Geologists |  |  | 2 | 20 | 40
Bring material |  |  | 70 | 280 |  | Surveyors |  |  | 1 | 30 | 30
Build manways |  |  | 120 | 480 |  | Mechanics & electricians |  |  | 1 | 15 | 15
Store material |  |  | 30 | 120 |  | Level ore with scraper |  |  | 4 | 240 | 960
|  |  |  | 0 |  | Repairs in main access |  |  | 1 | 20 | 20
|  |  |  | 0 | [6 empty] | 0
|  |  |  | 960 | minutes |  |  |  |  | minutes | 1065
|  |  |  | 16 | hours (manways) |  |  |  |  | hours | 17.75
Here are the most common steps | [6 empty] | Here are the most common steps in Shrinkage Stopes
in Shrinkage Stopes: | [6 empty] | with the raise outside the stope:
4.0 - DIRECT VARIABLE ACTIVITIES PER STEP (inside the stope)
4.1 - Lift Dimensions
| Breast |  |  | Lift |  |  | Slot raise
| parameters |  |  | parameters |  |  | parameters |  |  | ore density (t/m³)
2.95
| Drilled length | 3.65 |  | Length | 348 |  | Drilled length | 2.4
| Broken length | 3.55 |  | Height | 2.4 |  | Broken length | 2.35
| Height | 2.4 |  | Average width | 1.8 |  | Height | 2.3
| Width | 1.8 |  | # advances | 99 |  | Width | 1.8
| Tonnes/breast | 46 |  | Tonnes | 4435 |  | Tonnes | 29
Number of rounds/lift
3
4.2 - Scaling
| minutes/ |  |  |  | total hours
Wash, scale and clean bootlegs | longitudinal m | hours |  |  | (lift) |  |  | total hours
| 15 | 0.9 |  |  | 89.1 |  |  | 1.8
GROUND SUPPORT PARAMETERS
4.3 - Ground Support | [10 empty] | Drilled length/bolt | Number of bolts/1.2 m advanced | Drilled meters/m advanced
|  | hours |  |  | hours |  |  | hours
Drilling for support |  | 1 |  |  | 99 |  |  | 2 | Roof pattern |  | 1.2 | 2 | 2.1
| installation time/bolt (min) | [7 empty] | Hanging wall pattern |  | 1.2 | 2 | 2.1
|  | hours |  |  | hours |  |  | hours | Footwall pattern |  | 1.2 | 2 | 2.1
Installation of ground support | 3 | 1.1 |  |  | 108.9 |  |  | 2.2 |  |  |  | 6 | 6.3
(screen included) |  | total hours |  |  | total hours |  |  | total hours
|  | 2.1 |  |  | 207.9 |  |  | 4.2
4.4 - Drilling | [8 empty] | DRILLING PARAMETERS
[8 empty] | holes/round | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
[7 empty] | drilled | 32 | Time required for repositioning, changing drilling steel and bits, etc. per hole of 2.4 m (min) |  |  |  | 1.85
[7 empty] | blasted | 29
[9 empty] | Total average time to drill a 2.4-m hole (min) |  |  |  | 6.17
|  | meters |  |  | meters |  |  | meters | Average drilling rate |  |  |  | 23.3387
Meters to drill |  | 32.85 |  |  | 3252.15 |  |  | 230.4 | (drilled meters per hour/man/drill)
|  | hours |  |  | hours |  |  | hours | DRILLING PATTERN (breasts)
Time required for drilling (hours) |  | 1.5 |  |  | 139.4 |  |  | 9.9 | Number of holes per breast |  |  |  | 9
[10 empty] | tonnes/drilled meter |  | tonnes per hole
[10 empty] | 1.4003 |  | 5.1111
BLASTING PARAMETERS
4.5 - Loading and Blasting | [7 empty] | total hours (lift) |  | Hole diameter (mm) | 32 | Powder factor per breast (kg/tonne)
| average time/ hole (min) |  |  |  | total hours (lift) |  |  |  |  | Explosive density (g/cc) | 1.01
hours
Clean and load holes | 1.3 | 0.2 |  |  | 19.8 |  |  | 1.9 | Kg of explosives/meter |  | 0.81229 | 0.56419
Required explosives (kg) |  | 26 |  |  | 2502 |  |  | 49 |  | Number of blasts (lift) |  |  | 102
4.6 - Ventilation
(To use when blasting causes a delay during the shift or when the work schedule is 24 hours a day)
minutes required/
Ventilation | blast |  |  |  | total hours
(evacuation of fumes) | 0 |  |  |  | 0
5.0 - BREAST COMPILATION
TABLE OF REQUIRED HOURS PER BREAST
DIRECT ACTIVITIES
PER ADVANCE |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 0.33333 | 0.16667 | 0.15686 | 0.6 | 0 | 0.017157 | 1.274
DIRECT VARIABLE (hours) |  | 0.9 | 2.1 | 1.5 |  | 0.2 |  |  | 4.7
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 0.45 | 1.05 | 0.75 |  | 0.1 |  |  | 2.35
* The number of required hours is corrected according to the number of men entered in section 5.0. | [7 empty] | total : | 3.624
+
[8 empty] | contingency (ventilation included) | 10%
[8 empty] | allocated time for contingency | 21.7441 | minutes
=
[8 empty] | total time required inside the stope (contingency included) | 4 | hours
+
[8 empty] | total time of direct fixed activities outside the stope | 2.1833 | hours
| REQUIRED NUMBER OF MEN | 2 | [6 empty] | =
| NUMBER OF HOURS PER SHIFT | 8.5 | <=> |  |  |  |  | total time required per advance | 6.1833 | hours
[8 empty] | occupation rate of the stope per advance | 47.06%
[8 empty] | occupation rate of the shift per advance | 72.75%
5.1 - CALCULATION OF THE POSSIBLE NUMBER OF ADVANCES PER SHIFT ACCORDING TO ENTERED DATA:
In this section, you can optimize your operating parameters to simulate your operation or to find
the required parameters to reach the desired performance.
|  | Number of hours per shift | 8.5 |  | total time required inside the stope (contingency included)
-
|  | Direct fixed time outside the stope/shift | 2.1833 |  |  |  |  | Possible number of advances per shift
=
|  | Available time inside the stope/shift | 6.3167 | / | 4 |  | = | 1.5792
Is it possible to blast during the shift? If yes, optimize the parameters to obtain the desired results.
6.0 - LIFT COMPILATION
DIRECT ACTIVITIES PER LIFT |  | SCALING | SUPPORT | DRILLING | MUCKING | BLASTING | VENTILATION | MANWAYS | OTHERS | Scheduled hrs
DIRECT FIXED (hours) |  | see support | 34 | 17 | 16 | 61.2 | 0 | 16 | 1.75 | 145.95
DIRECT VARIABLE (hours) |  | 90.9 | 212.1 | 149.3 |  | 68.8 |  |  |  | 521.1
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 45.45 | 106.05 | 74.65 |  | 34.4 |  |  |  | 260.55
* The number of required hours is corrected according to the number of men entered in section 5.0. | [8 empty] | total : | 406.5
total
REQUIRED MANHOURS |  | 90.9 | 280.1 | 183.3 | 32 | 191.2 | 0 | 32 | 3.5 | 813
REQUIRED MANSHIFTS |  | 10.6941 | 32.9529 | 21.5647 | 3.7647 | 22.4941 | 0 | 3.7647 | 0.41176 | 95.6471
+
REQUIRED NUMBER OF MEN |  | 2 |  |  |  | with a contingency of | 10% |  | manshift contingency | 9.5647
NUMBER OF HOURS PER SHIFT |  | 8.5 | hours | [6 empty] | =
[9 empty] | required manshifts inside the stope | 105.2118
+
[9 empty] | required manshifts from direct fixed activities (outside the stope) | 36.3661
=
[9 empty] | total manshifts required | 141.5778
[8 empty] | with a performance of | 1.5792 | advance/shift
[5 empty] | From your best estimate, you can maintain | 1 | advance/shift
[5 empty] | which represents an occupation rate of the shift (contingency included) of | 63.32%
MANSHIFTS
| INSIDE THE STOPE |  |  |  | OUTSIDE STOPE | TOTAL |  |  | 4522 | tonnes
| PRODUCTIVE | CONTINGENCY | TOTAL (STOPE) |  | FIXED
| 141.9506 | 14.1951 | 156.1457 |  | 53.9712 | 210.1169 | PRODUCTIVITY |  | 21.5214 | tonnes/manshift
| 67.56% | 6.756% | 74.31% |  | 25.69% | 100%
Calculation of required manhifts with contingency |  |  |  | Calculation of number of shifts according to schedule |  |  |  |  | Calculation of number of shifts of direct fixed activities
Required manhours |  | 813 |  |  |  | Required manshifts with contingency | 105.2118 |  |  |  | Number of required shifts (schedule) | 70.7889
|  | / |  |  |  |  | / |  |  |  |  | x
Hours/shift |  | 8.5 |  |  |  | Available hours inside the stope | 6.3167 |  |  |  | Direct fixed hours/shift | 2.1833
|  | = |  |  |  |  | x |  |  |  |  | /
Required manshifts |  | 95.6471 |  |  |  | Hours/shift | 8.5 |  |  |  | Hours/shift | 8.5
|  | + |  |  |  |  | / |  |  |  |  | =
Contingency |  | 10% |  |  |  | Men | 2 |  |  |  | Number of shifts of | 18.183
|  | = |  |  |  |  | = |  |  |  | direct fixed activities (schedule)
Required manshifts |  | 105.2118 |  |  |  | Number of required shifts (schedule) | 70.7889
with contingency
Calculation of total number of required manshifts | [6 empty] | Calculation of the number of round per shift (slot raise)
Total number of required shifts |  | 70.7889 |  |  |  | Required time per round (hours) | 4.6648
|  | x |  |  |  |  | /
Men |  | 2 |  |  |  | Available hours inside the stope | 6.3167
|  | = |  |  |  |  | =
Required manshifts |  | 141.5778 |  |  |  | Number of rounds per shift | 1.3541
with a performance of |  | 1.5792 | advance/shift
Note on B101: Time required to scale one meter (the roof and the two walls) and to clean the bootlegs
Note on F88: Length to be mined without the main raise and the slot raises
Note on I53: Enter the time required to level the broken ore for the entire lift when done in a single step (must include mucking delays)
Note on J36: Enter the time required to level the ore for each breast (must include mucking delays)
RAISE
3
4
2
1
5
6
7
8
9
10
11
level of broken ore before step 1
Raise outside the stope
(Breasts)
Part A
Part B
RAISE
1
3
4
2
Typical mining steps by Breasts

## DRAWINGS
Version: February 8, 2002
Part A
Part B
RAISE
1
3
4
2
Typical mining steps by Breasts
RAISE
3
4
2
1
5
6
7
8
9
10
11
level of broken ore before step 1
Raise outside the stope
(Breasts)
Part A
Part B
RAISE
1
3
4
2
1
5
Typical mining steps by Uppers
RAISE
1
level of broken ore before step 1
Central raise
(Breasts)
1
2
2
approximately 50 m in length