## Track drift
TRACK DRIFT
Productivity
Version: Mai 14, 2004
1.0 - DIRECT FIXED ACTIVITIES PER SHIFT (outside the drift)
|  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  | NOTES
Cage (at beginning and end of shift) |  | 2 | 2 | 4
Travelling (shaft - refuge station - shaft) |  | 2 | 1 | 2
Other travelling delays |  |  |  | 0
Back and forth to drift |  | 4 | 2 | 8
Supervision |  | 1 | 15 | 15
Work planning |  | 1 | 2 | 2
Complete daily reports |  | 1 | 5 | 5
Lunch |  | 1 | 30 | 30
0
|  |  |  | 66 | minutes
|  |  |  | 1.1 | hours/shift
2.0 - DIRECT FIXED ACTIVITIES PER STEP (inside the drift)
RELATED TO MUCKING |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | RELATED TO TRACK |  | Frequency or Units | Time (min)/Unit | Total Time (min)
PREPARATION | [5 empty] | INSTALLATION
Check locomotive and cars |  | 1 | 3 | 3 |  | Prepare equipment and material |  | 1 | 5 | 5
Clean the face |  | 1 | 4 | 4 |  | Align the track |  | 1 | 6 | 6
Clean the ditch |  | 0.3 | 20 | 6 |  | Align and mark next round |  | 1 | 5 | 5
Clean and store equipment |  | 1 | 4 | 4 |  | Store material |  | 1 | 5 | 5
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 |  |  |  |  | minutes/track installation | 21
|  |  |  | 17 | minutes/mucking preparation |  |  |  | hours/track installation | 0.35
|  |  |  | 0.28333 | hours/mucking preparation
2.0 - (cont'd) DIRECT FIXED ACTIVITIES PER STEP (inside the drift)
RELATED TO GROUND |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  |  |  | Frequency or Units | Time (min)/Unit | Total Time (min)
SUPPORT | [5 empty] | RELATED TO BLASTING
Bring equipment and material |  | 1 | 5 | 5 |  | Bring explosives |  | 1 | 5 | 5
Install setup platform |  |  |  | 0 |  | Bring and prepare material |  | 1 | 6 | 6
Store material |  | 1 | 4 | 4 |  | Store equipment and explosives |  | 1 | 5 | 5
|  |  |  | 0 |  | Connect the blast |  | 1 | 8 | 8
|  |  | minutes/setup | 9 |  | Access verification |  | 1 | 5 | 5
|  |  | hours/setup | 0.15 |  | Extra scaling |  |  |  | 0
[6 empty] | Repair and install ventilation |  | 0.5 | 5 | 2.5
0
|  | Frequency or Units | Time (min)/Unit | Total Time (min) | [5 empty] | 0
RELATED TO DRILLING | [8 empty] | minutes/blast | 31.5
Prepare material |  | 1 | 2 | 2 |  |  |  |  | hours/blast | 0.525
Remove setup platform |  |  |  | 0
Clean the face to drill lifter holes |  | 1 | 3 | 3
Store equipment and material |  | 1 | 2 | 2
|  |  |  | 0 |  | RELATED TO |  | Frequency or Units | Time (min)/Unit | Total Time (min)
|  |  |  | 0 |  | SERVICES
|  |  | minutes/setup | 7 |  | Bring material |  | 1 | 5 | 5
|  |  | hours/setup | 0.11667 |  | Install pipes (water and air) |  | 0.275 | 30 | 8.25
[6 empty] | Install ventilation |  | 0.11 | 30 | 3.3
[6 empty] | Store material |  | 1 | 5 | 5
0
[9 empty] | minutes/setup | 21.55
[9 empty] | hours/setup | 0.35917
3.0 - DIRECT FIXED ACTIVITIES FOR THE ENTIRE DRIFT
RELATED TO MOBILIZATION |  | Frequency or Units | Time (min)/Unit | Total Time (min) |  | OTHER ACTIVITIES |  | Frequency or Units | Time (min)/Unit | Total Time (min)
AND DEMOBILIZATION | [5 empty] | PER DRIFT
Install ventilation ducts |  | 1 | 720 | 720 |  | Geologists |  | 37.5 | 20 | 750
Install electric panel |  | 1 | 720 | 720 |  | Surveyors |  | 7.5 | 30 | 225
Check services (water and air) |  | 1 | 180 | 180 |  | Mechanics and electricians |  | 7.5 | 30 | 225
Other repairs |  | 1 | 360 | 360 | [5 empty] | 0
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 | [5 empty] | 0
|  |  |  | 0 |  |  |  |  | minutes | 1200
|  |  |  | 1980 | minutes |  |  |  | hours | 20
|  |  |  | 33 | hours
RELATED TO SWITCH (only if a switch must be installed during the project)
INSTALLATION |  | Frequency or Units | Time (min)/Unit | Total Time (min)
Bring equipment and material |  | 1 | 30 | 30
Clean the floor |  | 1 | 35 | 35
Install switch |  | 1 | 240 | 240
0
0
|  |  |  | 305 | minutes
|  |  |  | 5.0833 | hours
4.0 - DIRECT VARIABLE ACTIVITIES PER STEP (inside the drift)
4.1 - Dimensions
| Round |  |  | Drift
| parameters |  |  | parameters
| Drilled length | 2.13 |  | Length | 300
| Broken length | 2 |  | Height | 2.7
| Height | 2.7 |  | Average width | 2.7 |  | ore density (t/m³)
| Width | 2.7 |  | # of rounds | 150 |  | 2.95
| Tonnes | 44 |  | Tonnes | 6452
4.2 - Mucking
| tonnes/hour | hours |  | tonnes/hour | hours
Mucking | 32 | 1.4 |  | 32 | 201.7
4.3 - Scaling
| minutes/ |  |  |  | total hours (drift)
Wash, scale and clean bootlegs | longitudinal meter | hours
| 3 | 0.1 |  |  | 15
4.4 - Ground Support | [5 empty] | DRILLING PARAMETERS (ground support)
[6 empty] | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
|  | hours |  |  | hours | Time required for repositioning, changing drilling steel and bits, etc. per hole of 1.2 m (min) |  |  |  | 0.4
Drilling for support |  | 0.7 |  |  | 105
| installation time/bolt (min) |  |  |  |  | Total average time to drill a 1.2-m hole (min) |  |  |  | 2.56
|  | hours |  |  | hours
Installation of ground support | 0.45 | 0.2 |  |  | 30 | Average drilling rate |  |  |  | 28.125
(screen included) |  | total hours |  |  | total hours | (drilled meters per hour/man/drill)
|  | 0.9 |  |  | 135
GROUND SUPPORT PARAMETERS
[8 empty] | Drilled length/bolt | Number of bolts/1.2 m advanced | Drilled meters/m advanced
[6 empty] | Roof pattern |  | 1.67 | 3 | 4.3
[6 empty] | Hanging wall pattern |  | 1.3 | 2 | 2.3
[6 empty] | Footwall pattern |  | 1.3 | 2 | 2.3
[9 empty] | 7 | 8.9
4.5 - Track | [5 empty] | Installation of 2 rails of |  | 20 | feet
| linear m/hour | hours |  |  | hours | Track installation |  | minutes
Clean the floor | 50 | 0.1 |  |  | 15 | Remove side rails |  | 8
[6 empty] | Install 6 ties |  | 10
| linear m/hour | hours |  |  | hours | Install 2 rails |  | 15
Install track | 5.9 | 0.4 |  |  | 60 | Install 2 fish plates |  | 6
[6 empty] | Install 12 spikes |  | 20
|  | total hours |  |  | total hours | Check the track clearance |  | 3
|  | 0.5 |  |  | 75 |  |  | 62 | minutes/20 feet
[8 empty] | 5.9 | meters/hour
4.6 - Drilling | [5 empty] | DRILLING PARAMETERS (advance)
[6 empty] | Time required to drill a 1.2-m hole (min) |  |  |  | 2.16
| drilled holes/round |  |  |  |  | Time required for repositioning, changing drilling steel and bits, etc. per hole of 2.4 m (min) |  |  |  | 2
42
|  | meters |  |  | meters | Total average time to drill a 2.4-m hole (min) |  |  |  | 6.32
Meters to drill |  | 89.46 |  |  | 13419
|  | hours |  |  | hours | Average drilling rate |  |  |  | 22.7848
Time required for drilling (hours) |  | 4 |  |  | 589 | (drilled meters per hour/man/drill)
tonnes/drilled meter
0.49184
4.7 - Loading and Blasting |  | holes/blast |  |  |  | BLASTING PARAMETERS
|  | 39 |  |  |  |  | Hole diameter (mm) | 32 | Powder factor per round (kg/tonne)
| average time/ hole (min) |  |  |  | total hours (drift) |  | Explosive density (g/cc) | 1.01
hours
Clean and load holes | 1.3 | 1 |  |  | 150 | Kg of explosives/meter |  | 0.81229 | 1.6515
Required explosives (kg) |  | 73 |  |  | 10656 |  | Number of blasts (drift) |  |  | 150
4.8 - Ventilation
(To use when blasting causes a delay during the shift or when the work schedule is 24 hours a day)
minutes required
Ventilation | /blast |  |  |  | total hours
(evacuation of fumes) |  |  |  |  | 0
5.0 - ROUND COMPILATION
TABLE OF REQUIRED HOURS PER ROUND
DIRECT ACTIVITIES |  |  | SCALING
PER ADVANCE |  | MUCKING | SUPPORT | TRACK | DRILLING | BLASTING | VENTILATION | OTHERS | Scheduled hours
DIRECT FIXED (hours) |  | 0.28333 | 0.15 | 0.35 | 0.11667 | 0.525 | 0 | 0.4925 | 1.9175
DIRECT VARIABLE (hours) |  | 1.4 | 1 | 0.5 | 4 | 1 |  |  | 7.9
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 1.4 | 0.5 | 0.25 | 2 | 0.5 |  |  | 4.65
* The number of required hours is corrected according to the number of men entered in section 5.0. | [7 empty] | total: | 6.5675
+
[8 empty] | contingency (ventilation included) | 5%
[8 empty] | allocated time for contingency | 19.7025 | minutes
=
[8 empty] | total time required inside the drift (contingency included) | 6.9 | hours
+
[8 empty] | total time of direct fixed activities outside the drift | 1.1 | hours
| REQUIRED NUMBER OF MEN | 2 | [6 empty] | =
| NUMBER OF HOURS PER SHIFT | 8 | <=> |  |  |  |  | total time required per advance | 8 | hours
[8 empty] | occupation rate of the shift per advance | 100%
5.1 - CALCULATION OF THE POSSIBLE NUMBER OF ADVANCES PER SHIFT ACCORDING TO ENTERED DATA:
In this section, you can optimize your operating parameters to simulate your operation or to find
the required parameters to reach the desired performance.
|  | Number of hours per shift | 8
|  |  | - |  | total time required inside the drift (contingency included)
|  | Direct fixed time outside the drift/shift | 1.1 |  |  |  |  | Possible number of advances per shift
=
|  | Available time inside the drift/shift | 6.9 | / | 6.9 |  | = | 1
Is it possible to blast during the shift? If yes, optimize the parameters to obtain the desired results.
6.0 - DRIFT COMPILATION
SCALING
DIRECT ACTIVITIES PER DRIFT |  | MUCKING | SUPPORT | TRACK | DRILLING | BLASTING | VENTILATION | OTHERS |  | Scheduled hours
DIRECT FIXED (hours) |  | 42.5 | 22.5 | 57.5833 | 17.5 | 78.75 | 0 | 106.875 |  | 325.7083
DIRECT VARIABLE (hours) |  | 201.7 | 150 | 75 | 589 | 150 |  |  |  | 1165.7
ONLY DIRECT VARIABLE ACTIVITIES ARE INFLUENCED BY THE NUMBER OF MEN.
THEREFORE, ACCORDING TO THE NUMBER OF MEN ENTERED, WE OBTAIN:
DIRECT VARIABLE (hours) * |  | 201.7 | 75 | 37.5 | 294.5 | 75 |  |  |  | 683.7
* The number of required hours is corrected according to the number of men entered in section 5.0. | [8 empty] | total: | 1009.4083
total
REQUIRED MANHOURS |  | 488.4 | 195 | 190.1667 | 624 | 307.5 | 0 | 213.75 |  | 2018.8167
REQUIRED MANSHIFTS |  | 61.05 | 24.375 | 23.7708 | 78 | 38.4375 | 0 | 26.7188 |  | 252.3521
+
REQUIRED NUMBER OF MEN |  | 2 |  |  |  | with a contingency of | 5% |  | manshift contingency | 12.6176
NUMBER OF HOURS PER SHIFT |  | 8 | hours | [6 empty] | =
[9 empty] | required manshifts inside the drift | 264.9697
+
[9 empty] | required manshifts from direct fixed activities (outside the drift) | 42.2415
=
[9 empty] | total manshifts required | 307.2112
[8 empty] | with a performance of | 1 | advance/shift
|  |  |  | From your best estimate, you can maintain | 1 | advance/shift
|  |  |  | which represents an occupation rate of the shift (contingency included) of | 100%
MANSHIFTS
| INSIDE THE DRIFT |  |  |  | OUTSIDE DRIFT | TOTAL |  |  | 6452 | tonnes
| PRODUCTIVE | CONTINGENCY | TOTAL (DRIFT) |  | FIXED
| 296.8536 | 14.8427 | 311.6963 |  | 49.6907 | 361.387 | PRODUCTIVITY |  | 17.8534 | tonnes/manshift
| 82.14% | 4.107% | 86.25% |  | 13.75% | 100%
[9 empty] | 0.83014 | meter/manshift
Monthly planning factors:
[5 empty] | ENTER THE AVERAGE PERCENTAGE OF ADVANCES ACHIEVED ON A MONTHLY BASIS | 85% |  | 28.2246 | meters advanced/month
[5 empty] | NUMBER OF SHIFTS/MONTH | 20 |  | 1214.0339 | tonnes/month
Calculation of required manhifts with contingency |  |  | Calculation of number of shifts according to schedule |  |  |  | Calculation of number of shifts of direct fixed activities
Required manhours | 2018.8167 |  |  | Required manshifts with contingency | 264.9697 |  |  | Number of required shifts (schedule) | 153.6056
| / |  |  |  | / |  |  |  | x
Hours/shift | 8 |  |  | Available hours inside the drift | 6.9 |  |  | Direct fixed hours/shift | 1.1
| = |  |  |  | x |  |  |  | /
Required manshifts | 252.3521 |  |  | Hours/shift | 8 |  |  | Hours/shift | 8
| + |  |  |  | / |  |  |  | =
Contingency | 5% |  |  | Men | 2 |  |  | Number of shifts of | 21.1208
| = |  |  |  | = |  |  | direct fixed activities (schedule)
Required manshifts | 264.9697 |  |  | Number of required shifts (schedule) | 153.6056
with contingency
Calculation of total number of required manshifts
Total number of required shifts | 153.6056
x
Men | 2
=
Required manshifts | 307.2112
with a performance of | 1 | advance/shift
Note on B112: see"FACE CLEANING_RAILS" file
Note on B118: Time required to scale one meter (the roof and the two walls) and to clean the bootlegs
Note on C195: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE DRIFT
Note on C232: NOT PROPORTIONAL TO THE NUMBER OF MEN INSIDE THE DRIFT
Note on E112: see "FACE CLEANING_RAILS" file

## Costs per meter
Unit cost model for track drift
|  |  |  | Reference case |  |  | Your case
1 - Labour
Hourly rate: |  |  |  |  | 57.5 | $/hour |  | 55 | $/hour
including basic salary, bonus, fringe benefits
Number of hours per shift |  |  |  |  | 8 | hours |  | 8 | hours
Productivity |  |  |  |  | 0.97 | m/manshift |  | 2 | m/manshift
[5 empty] | 474.2268 | $/meter |  | 220 | $/meter
2 - Material |  |  |  |  | $/meter |  |  | $/meter
Drilling (jackleg drills and stoper) |  |  |  |  | 80.84 |  |  | 80.84
steel rods, bits, hoses, lubricants
Explosives and accessories |  |  |  |  | 107.19 |  |  | 107.19
Support
mechanical rockbolts |  |  |  | 54 |  |  | 54
rebars and resin |  |  |  | 0.05 |  |  | 0.05
Split-Set
Swellex
screen |  |  |  | 6.29 |  |  | 6.29
cables and ciment
shotcrete
| total support | total support |  | 60.34 | 60.34 |  | 60.34 | 60.34
Timber |  |  |  |  | 15.31 |  |  | 15.31
Track
rails, spikes, fish plates |  |  |  | 54 |  |  | 54
ties |  |  |  | 0.05 |  |  | 0.05
switch
ditch
crushed stone |  |  |  | 6.29 |  |  | 6.29
others
|  |  | total track | 60.34 | 60.34 |  | 60.34 | 57.81
Pipes |  |  |  |  | 29.55 |  |  | 29.55
Ventilation |  |  |  |  | 5.45 |  |  | 5.45
Diesel and lubricants |  |  |  |  | 0 |  |  | 0
Other supplies |  |  |  |  | 3.26 |  |  | 3.26
[5 empty] | 362.28 |  |  | 359.75
3 - Equipment maintenance
mechanical |  |  |  |  | 104.35 |  |  | 104.35
electrical |  |  |  |  | 12.05 |  |  | 12.05
Total per meter |  |  |  |  | 952.9068 |  |  | 696.15
Excluded costs | [5 empty] | Remarks:
- supply of compressed air and electricity | [5 empty] | The reference case is a 2.7 m by 2.7 m
- supply of drilling water | [5 empty] | drift drilled with Long Tom and cleaned
- supervision | [5 empty] | with a LM56 mucking machine
- equipment amortization | [5 empty] | and 5-tonne cars.
- general level maintenance
Note on F26: Enter the global support cost if details are not available
Note on F37: Enter the global track cost if details are not available
Note on I26: Enter the global support cost if details are not available
Note on I37: Enter the global track cost if details are not available